## Workplan 2018-19
MYANMAR EITI PROJECT PHASE II
3-YEAR MASTER PLAN (2017 TO 2019)
Strategic Goals: To promote transparency and accountability in the extractive industries and material revenue management of the Union of Myanmar. (in line with the National Economic Policy 1 and 2, laid down by the Republic of the Union of Myanmar)
|  |  | Implementing Agency | Category of Expense | Outputs | KPI |  | 2017 | Q-1'18 | Q-2'18 | Q-3'18 | Q-4'18 | 2018 Total | Q 1 | Q 2 | Q 3 | Q 4 | 2019 Total | 2018 | [7 empty] | 2019
Activity No. | Category of Activity | Activities |  |  |  |  | TOTAL BUDGET | Actual | Actual | Budget | Budget | Budget | Budget | Budget | Budget | Budget | Budget | Budget | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Responsible Party | Status
Objective 1: To acquire & disseminate accurate, correct and up-to-date information regarding the management of natural resources and associated material revenues in a timely manner and to make the information publicly available
1.1 | Communication and Outreach
1.1.1 | MEITI Report Launch | Report Print | NCS Communication, Communication and Outreach Sub-Committee | Goods | Printed copies of report (Executive Summary, Full Report, Myanmar Version, English Version) | No. of copies of each version printed No. of copies of each version distriubuted | 50000 | 0 | 0 | 35000 |  |  | 35000 |  |  |  |  | 15000 | [20 empty] | NCS/MSG | Underway
1.1.2 | Forestry Report Launch | Report Print | NCS Communication, Communication and Outreach Sub-Committee | Goods | Printed copy of Forestry Report (Myanmar and English version) | No. of copies of each version printed No. of copies of each version distriubuted | 15000 |  |  | 15000 |  |  | 15000 | [25 empty] | NCS/MSG | Underway
1.1.3 | MEITI Report Launch | Media including TV, Radio, events and activities includign press release | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased knowledge of EITI and extractives in Myanmar | No. of events, TV /Radio Programs/ Media Articles No. and details of participants and audiences (gender, geographical location, ethnicity etc) Event Reports / quaility (accuracy of media reports) | 45000 |  |  | 18000 | 7000 |  | 25000 |  |  |  |  | 20000 | [20 empty] | NCS/MSG | Underway
1.1.4 | Forestry Report Launch | Media including TV, Radio, events and activities includign press release | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased knowledge of Forestry extractives in Myanmar | No. of events, TV /Radio Programs/ Media Articles No. and details of participants and audiences (gender, geographical location, ethnicity etc) Event Reports / quaility (accuracy of media reports) | 15000 |  |  |  | 6000 | 3000 | 9000 |  |  |  |  | 6000 | [20 empty] | NCS/MSG | Underway
1.1.5 | Public Debates | Public Gathering/ debate and Road Show | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased knowledge of EITI and extractives in Myanmar | No. of public gatherings, debates, roadshow events No. and details of participants Event Feedback and Reports | 40000 |  |  | 10000 |  | 0 | 10000 |  |  |  |  | 30000 | [20 empty] | NCS/MSG | Underway
1.1.6 | Prints and Publication | Other prints and IEC material development | NCS Communication, Communication and Outreach Sub-Committee | Goods | IEC Materials | No and type of materials produced No and type of materails distributed/ viewed online Feedback on materials (?) | 41999.98 | 6666.98 |  | 10000 | 5093 |  | 15093 |  |  |  |  | 20240 | [20 empty] | NCS/MSG | Underway
1.1.7a. | Website | Redesign, regular update and maintenance MEITI Website & on-line library | NCS Communication, Communication and Outreach Sub-Committee | Non Consulting Services | Website | No. of hits on website Feedback Survey Validation Comments | 6627 | 1627 | 0 | 4000 |  |  | 4000 | 0 | 0 | 0 | 0 | 1000 | [20 empty] | M.Spiral/NCS | Underway
1.1.7b. | Video Production and Broadcasting | Video Production and Broadcasting | NCS Communication, Communication and Outreach Sub-Committee | Non Consulting Services | Videos | Number of views, boradcasts, feedback | 15000 |  |  | 15000 |  |  | 15000 | [25 empty] | MSG/NCS | Underway
1.1.8 | Web-portal and Infographic | Open data, Inforgraphic and updated data | NCS Communication, Communication and Outreach Sub-Committee | Non Consulting/ Consulting | Infographics and open data pages | No. of users Feedback and Validation Comments | 10000 |  |  | 5000 |  |  | 5000 |  |  |  |  | 5000 | [20 empty] | Ko Yan Naung Oak/NCS | Underway
1.1.9 | National EITI Conference | National EITI Conference | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased understanding of MEITI Improved multistakeholder participation Documented assessment of progress, Input for planning | Event Report No. and details of participants Progress assessment and Planning input Feedback from participants | 15000 |  |  |  |  | 7500 | 7500 | 0 |  |  |  | 7500 | [20 empty] | MSG/NCS | Not Yet
Sub Total 1 | [6 empty] | 253626.98 | 8293.98 | 0 | 112000 | 18093 | 10500 | 140593 |  |  |  |  | 104740 | [22 empty] | 253626.98
Objective 2: To create an enabling environment for the effective implementation of the EITI Standard
2.1 | HR, Operation and Office Administration
2.1.1 | MOBD Operational Cost | MOBD Staff travel and Office Supplies | MOBD | Operating Cost/ Goods | Project Financial Management, Procurement and Grant Compliance | FM reports to MSG and Donors, Procurement Plans and Documentation OAG Audit LC and WC Support to EITI process | 57000 | 2288 | 2207 | 7505 | 7500 | 7500 | 24712 | 0 | 0 | 0 | 0 | 30000 | [20 empty] | MOBD | Underway
2.1.2 | NCS Operation Cost | NCS Staff Salaries | NCS | Operating Cost | Successful Implementation of Work Plan activities | APR EITI Reconciliation Reports MSG and Subcommittee Minutes Staff Performance Evaluations | 291400 | 65067 | 45421 | 49200 | 49200 | 49200 | 193021 | 0 | 0 | 0 | 0 | 33312 | [20 empty] | NCS/MOBD | Underway
2.1.3a. | NCS Operation Cost | NCS Overheads ( Utilities, Travel, Communication service, Maintenance, Stationary, consumable material and other miscellaneous) | NCS | Operating Cost | Successful Implementation of Work Plan activities | APR EITI Reconciliation Reports MSG and Subcommittee Minutes | 79300 | 17019 | 22783 | 9000 | 9000 | 9000 | 49783 | 0 | 0 | 0 | 0 | 12498 | [20 empty] | NCS/MOBD | Underway
2.1.3b. | Consultant support service | Additional Travel and Accommodation costs to support consultants (BO, Cadastre etc) | NCS | Operating Cost | Facilitation of Consultants' Work | Consultant Deliverables | 31500 |  |  | 4500 | 4500 | 4500 | 13500 |  |  |  |  | 18000 | [20 empty] | NCS/MOBD | Underway
2.1.4 | NCS Operation Cost | NCS Office Rental | NCS | Operating Cost | Office Space | Office Rental Contract and Payment Reciept | 36000 | 9032 | 4500 | 4500 | 4500 | 4500 | 18000 | 0 | 0 | 0 | 0 | 8968 | [20 empty] | NCS/MOBD | Underway | 438200
2.1.5 | Office Set Up Cost | Equipment and Furniture | NCS, MOBD | Goods | Furniture and Equipment | Purchase Receipts Procurement Report Inventory | 21000 | 9959 | 4524 | 0 |  |  | 4524 |  |  | 0 | 0 | 6517 | [20 empty] | NCS/MOBD | Underway |  | 8500
2.1.6 | Fund raising | Secure alternative funding from development partners | MSG, NCS | Workshop and Meeting | Funds raised | Meeting Minutes Workshop Reports Funds Raised | 1000 |  |  |  |  | 1000 | 1000 |  |  |  |  | 0 | [20 empty] | NCS/MOBD | Underway
2.1.7 | Fund raising- Advocacy | Secure increased government contribution to EITI | MOBD, MSG | Non Consulting |  |  | 3000 | 0 |  |  |  | 2000 | 2000 | 0 |  |  |  | 1000 | [20 empty] | NCS/MOBD | Underway
2.1.8 | MSG Meeting | MSG Meeting | NCS | Workshop and Meeting | MSG Meeting Decisions and Outputs (approved TOR, reports etc) | Meeting Minutes Approved (Myanmar and English) Minutes posted on MEITI Website Funds Raised | 111400 | 16799 | 14760 | 11400 | 11400 | 11400 | 48960 | 0 | 0 | 0 | 0 | 45641 | [20 empty] | MSG/NCS/MOBD | Underway
2.1.9 | Sub-committee Meeting | MSG Sub-Committee Meetings | NCS | Workshop and Meeting | Subcommittee Meeting Recommendations and Outputs (draft TOR, reports etc) | Meeting Minutes Approved (Myanmar and English) Minutes posted on MEITI Website Funds Raised | 48700 | 5434 | 1201 | 6000 | 6065 | 6000 | 19266 | 0 | 0 | 0 | 0 | 24000 | [20 empty] | Subcommittees/NCS/MOBD | Underway
Sub Total 2.1 | [6 empty] | 680300 | 125598 | 95396 | 92105 | 92165 | 95100 | 374766 |  |  |  |  | 179936 | [22 empty] | 680300
2.2 | Workplan and Governance (APR, M&E- Review workshops)
2.2.1 | M&E | Review of annual progress (workplan), produce annual activity/progress report. | NCS, MSG | Workshop and Meeting | Increased understanding of MEITI Improved multistakeholder participation Documented assessment of progress, Input for planning | Event Report No. and details of participants Progress assessment and Planning input Feedback from participants | 12000 | 0 |  | 6000 |  |  | 6000 |  | 0 |  |  | 6000 | [20 empty] | MSG/NCS | Underway
2.2.2 | Implementation of the recommendations from EITI reports | Workshop to develop the workplan for implementation of EITI recommendations | MOBD, NCS, Subcommittee, MSG | Workshop and meeting | Systematic assessment of EITI Recommendations from reports and planning for their implementation | SMART Work Plan for implementation Recommendations | 12000 | 0 |  | 3000 | 3000 | 0 | 6000 | 0 |  |  |  | 6000 | [20 empty] | MSG/NCS | Underway
2.2.3 | Implementation of the recommendations from EITI reports | Implement the workplan for EITI recommendations | NCS, MSG, Government Agencies | Workshop and meeting/ Consultancy/ Goods | Outputs according to the agreed work plan | Indicators according to the agreed work plan | 50000 |  |  | 10000 | 10000 |  | 20000 |  |  |  |  | 30000 | [20 empty] | MSG/NCS | Underway
2.2.4 | SOE Reform Workshop | Two-day workshop on SOE situations and future reform plans for extractor sector | MOBD, NCS, Subcommittee, MSG | Workshop and Meeting | Increased awareness of MEITI Report recommendtions on SOE Reform Documented multi-stakeholder review of current SOE reform plans, achievements and challenges Plans for ongoing reforms and their coordination with MEITI | Workshop Report incl participation Documentation of assessments, decisions and plans | 10000 | 0 |  | 10000 |  |  | 10000 |  |  |  |  | 0 | [20 empty] | MSG/NCS | Underway
2.2.5 | Validation | Data Collection and Stakeholder Consultation workshops for initial assessment | NCS, MSG | Workshop and meeting | Multistakeholder assessment and documentation of MEITI process Capacity Building for MEITI Stakeholders | Validation Report | 15000 |  |  | 10000 | 5000 |  | 15000 |  |  |  |  | 0 | [20 empty] | MSG/NCS/MOBD | Not Yet
2.2.6 | Validation | implement activities to address recommendation from Validation |  |  |  |  | 10000 | [10 empty] | 10000 | [20 empty] | MSG/NCS/MOBD | Not Yet
2.2.7 | Validation | Contribution to International Secretariat | MOBD, NCS |  | Payment made | Money transfer receipt, Bank Transaction Sheet, letter of acknowledgement from EITI | 10000 |  |  | 10000 |  |  | 10000 |  |  |  |  | 0 | [20 empty] | MSG/NCS/MOBD | Not Yet
Sub Total 2.2 | [6 empty] | 119000 | 0 | 0 | 49000 | 18000 | 0 | 67000 | 0 | 0 | 0 | 0 | 52000 | [22 empty] | 119000
2.3 | Sub-National Coordination Unit (Formation and Functioning)
2.3.1 | SNU Formation and Coordination | Establishing Sub-National Coordination Units at State and Division level and further coordination with Union EITI. | NCS, MSG, Communication Officer | Workshop and meeting | SNUs Formed (Membership, TOR) Meeting Records / Minutes/ Reports | No. of SNUs Formed SNU Membership details (inclusivity, participation, geographic coverage) SNU TORs and Work Plans | 100000 | 0 | 10633 | 16926 | 22000 | 16000 | 65559 | 0 | 0 | 0 | 0 | 34441 | [20 empty] | MSG/NCS | Underway
2.3.2 | SNU Operational Cost (just operations) | Supporting regular meetings by SNUs | MOBD, NCS, MSG, SNUs | Workshop and meeting | SNU Meetings Held Meeting Minutes SNU activities conducted (according to Workplan?) | No. of meetings Participation, Gender, Geogrpahic Coverage etc Indicators according to SNU Objectives and activities | 21000 |  |  |  |  | 5000 | 5000 | 0 | 0 | 0 | 0 | 16000 | [20 empty] | MSG/NCS/MOBD | Underway
2.3.3 | Coordination between MSG and SNUs | Review and evaluate reports from SNUs and determine coordinate consistent response to issues raised. MSG to establish internal monitoring and evaluation mechanism on workplan implementation?? | NCS, MSG, SNU |  | ??? | ??? | 10000 | 0 |  |  |  | 5000 | 5000 |  |  | 0 |  | 5000 | [20 empty] | MSG/NCS | Underway
Sub Total 2.3 | [6 empty] | 131000 | 0 | 10633 | 16926 | 22000 | 26000 | 75559 |  |  |  |  | 55441 | [22 empty] | 131000
Sub Total 2 |  |  |  | Sub Total 2 |  |  | 930300 | 125598 | 106029 | 158031 | 132165 | 121100 | 517325 |  |  |  |  | 287377 | [22 empty] | 930300
Objective 3:To support implementation of sustainable development and natural resource governance reforms through the successful execution of EITI.
3.1 | Technical and Reporting (IA main report, Forestry, BO, Mining Cadaster, SOE, Review of Artisenal Mining, Fasibility studies, Sub-national study, Implementation of recommendations, & other technical studies)
3.1.1 | Legislative institutionalization | Research to recommend legal options to EITI institunalization. | NCS, Subcommittee, MSG | Consultancy | Research Report and Recommendations | Research Report and Recommendations accpeted by MSG | 25000 | 0 |  |  |  | 25000 | 25000 |  |  |  |  | 0 | [20 empty] | MSG/Working Committee/NCS | Underway
3.1.2 | Legislative institutionalization | Developing a draft EITI Law or amemdments to Sectoral Laws | NCS, Subcommittee, MSG | Consultancy | Recommendations from above report implemented | Indicators related to each recommendation | 20000 | 0 |  |  | 10000 | 10000 | 20000 | [25 empty] | MSG/Working Committee/NCS | Underway
3.1.3 | EITI Reconciliation Report (Main report) | Independent Administrator and procure firm each year for the annual report (including scoping study) | MOBD, NCS, IA | Consulting | EITI Reconciliation Reports | Reports produced by deadline Reports approved by MSG Validation results on EITI Standard 2-6 | 436800 | 110740 | 83055 | 83005 |  |  | 166060 | 0 |  |  |  | 160000 | [20 empty] | MSG/NCS/MOBD | Underway
| EITI Reconciliation Report (Hydro Power IA report) | Independent Administrator and procure firm each year for the annual report (including scoping study) |  |  |  |  | 160000 | [10 empty] | 160000
3.1.4 | EITI Reconciliation Report | Report reconciliation and Reporting entities workshops-Main IA |  |  |  |  | 30000 | 14923 |  | 0 |  |  | 0 |  |  |  |  | 15077 | [20 empty] | MSG/NCS/MOBD | Underway
3.1.5 | Forestry Reconciliation Report | IA - First report |  | Consulting | Forestry Reconconciliation Report(s) | Report(s) approved by MSG | 160000 | 0 | 48301 | 111699 |  |  | 160000 |  |  |  |  | 0 | [20 empty] | MSG/NCS/MOBD | Underway
3.1.6 | Forestry Reconciliation Report | Reporting entities workshops-Forestry IA |  |  |  |  | 7300 |  | 3651 |  |  |  | 3651 |  |  |  |  | 3649 | [20 empty] | MSG/NCS/MOBD | Underway
3.1.7 | Mineral and Gemstone Cadaster | Design Phase | MONREC, NCS, Subcommitte, MSG | Consulting | Preliminary, Intermediate and Final Report Mineral Cadastre Conceptual Design TOR for Phase 2 | Documents received and approved by MONREC and MSG | 120000 | 40017 | 40024 | 39959 |  |  | 79983 |  |  |  |  | 0 | [20 empty] | MONREC/NCS | Underway
3.1.8 | Mineral and Gemstone Cadaster | Pre-cadaster Working Group Consultant | MONREC, NCS, Subcommitte, MSG | Consulting | Training and on the job support Precadastre developed | No. of staff trained No. of Training Hours completed Completeness of Precadastre | 26000 | 0 |  |  | 26000 |  | 26000 | 0 |  |  |  | 0 | [20 empty] | MONREC/NCS/MOBD | Not Yet
3.1.9 | Mineral and Gemstone Cadaster | Development and installation of cadaster. | MONREC, NCS, Subcommitte, MSG | Consulting | Deliverables outlined in TOR for Phase 2 | Indicators according to deliverables from TOR Phase 2 | 458000 | 0 |  |  |  | 200000 | 200000 | 0 |  |  |  | 258000 | [20 empty] | MONREC/NCS/MOBD | Not Yet
3.1.10 | Mineral and Gemstone Cadaster | Purchase of IT equipment and furniture | MONREC, NCS, MOBD | Goods | Equipment and Furniture | Procurement report Purchase Receipt Inventory | 400000 | 0 |  |  |  |  | 0 |  |  |  |  | 400000 | [20 empty] | MONREC/NCS/MOBD | Not Yet
3.1.11 | Research Study | SOE Structure Research | IA, NCS, Subcommittee, MSG | Consulting | Research Report and Recommendations | Report approved by MSG | 30000 | 0 |  |  |  | 30000 | 30000 |  | 0 |  |  | 0 | [20 empty] | MSG/NCS | Not Yet
3.1.12 | Research Study | EITI related research according to MSG including Feasibility Study (Hydro/ Fishery, etc) | NCS, Subcommittee, MSG | Consulting | Research Report and Recommendations | Report approved by MSG | 40000 | 0 |  |  |  | 25000 | 25000 |  |  | 0 |  | 15000 | [20 empty] | MSG/NCS | Underway
3.1.13a. | Beneficial Ownership | Development of Workplan, Communicaiton Plan, Capacity Building Plan and Pilot Project | NCS, Subcommittee, MSG | Consultancy | BO Work Plan, BO Communications Plan, BO Capacity Development Plan, BO Pilot Project | Deliverables approved by MSG | 120000 | 0 | 36000 | 84000 |  |  | 120000 |  |  |  |  | 0 | [20 empty] | Adam Smith Intel. | Underway
3.1.13b. | Beneficial Ownership | Domestic Consultant | NCS, Subcommittee, MSG | Consultancy |  |  | 36000 | 0 |  |  | 6000 | 6000 | 12000 |  |  |  |  | 24000 | [20 empty] | MSG/NCS/MOBD | Not Yet
3.1.14 | Beneficial Ownership Meetings | BO workshops and Taskforce Meetings | NCS, Task Force | Meeting and Workshop |  | No. of workshop/ meeting | 30000 | 0 |  | 10000 | 10000 | 10000 | 30000 |  |  |  |  | 0 | [20 empty] | BO Task Force/NCS | Not Yet
Sub Total 3.1 | [6 empty] | 2099100 | 165680 | 211031 | 328663 | 52000 | 306000 | 897694 |  |  |  |  | 1035726 | [22 empty] | 2099100
3.2 | Training and Capacity Development (Capacity Development for 3 MSG entities, MOBD, NCS & SNU capacity building)
3.2.1 | Capacity Development (MSG, Private Sector, Governemnt, CSO, Media, EAOs, MOBD, NCS, SNU, Parliament and others) | Implement Capacicty Development Plan, Oil and Gas Fiscal Regime, Revenue Collection Model and SOE Transparency and Reform, Mining and Gems Governance | NCS, MSG | Meeting and Workshop | Outputs defined in capacity development plan | Indicators defined in Capacity Development Plan Incld No. of participants, participant criteria (gender, stakeholder group, geographic location etc) Participant feedback | 111972.7 | 8267.7 | 7375 | 20000 | 33500 | 20357 | 81232 |  |  |  |  | 22473 | [20 empty] | MSG/NCS | Underway
3.2.2 | Capacity Development- Study Tour | MSG Study Tours (Zambia trip and Indonesia study tour) | MSG | Non Consulting | Outputs defined in Study Tour Concept Note or Plan | Indicators from concpet note or plan Incld No. of participants, participant criteria (gender, stakeholder group, geographic location etc) Participant feedback and cascading activities | 45000 | 0 |  | 20000 | 15000 |  | 35000 | 0 |  |  | 0 | 10000 | [20 empty] | MSG/NCS | Underway
3.2.3 | Capacity Development- EITI events | EITI Global/ Regional Conferences and Board Meetings | MSG | Non Consulting | EITI Internnational Events attended | No. of events attended, No. of participants, cascade activities | 30000 | 0 |  |  |  |  | 0 |  |  | 0 |  | 30000 | [20 empty] | MSG/NCS/MOBD | Not Yet
3.2.4 | Financial Management Training (MOBD) | MOBD Financial management capacity development | NCS, Subcommittee, MSG | Consulting | Training and on the job support | No. of MOBD staff trained | 30000 | 0 | 5952 | 9048 | 7500 | 7500 | 30000 |  |  |  |  | 0 | [20 empty] | MOBD | Implemented
Sub Total 3.1 | [6 empty] | 216972.7 | 8267.7 | 13327 | 49048 | 56000 | 27857 | 146232 |  |  |  |  | 62473 | [22 empty] | 216972.7
Sub Total 3 |  |  |  | Sub Total 3 |  |  | 2316072.7 | 173947.7 | 224358 | 377711 | 108000 | 333857 | 1043926 |  |  |  |  | 1098199 | [22 empty] | 2316072.7
GRAND TOTAL |  |  |  | Grand Total |  |  | 3499999.68 | 307839.68 | 330387 | 647742 | 258258 | 465457 | 1701844 |  |  |  |  | 1490316 | [22 empty] | 3499999.68
Projected Budget % against total budget | [7 empty] | 8.795% |  |  |  |  | 48.62% |  |  |  |  | 42.58%
% of Budget Allocation on Grant Amount
Objective 1 (Communication and Outreach)
Objective 2 (Operation, Overhead and Governance&WP)
Objective 3 (Technical & Reporting)
Objective 3 (Capacity Building)
Note on J54: MacBook Air: 30% paid
Note on S67: Reduced by 4,027 to balance total budget