## Clean Version (hidden)
MYANMAR EITI PROJECT PHASE II
3-YEAR MASTER PLAN & BUDGET (2017-2019)
Strategic Goals: To promote transparency and accountability in the extractive industries and material revenue management of the Union of Myanmar. (in line with the National Economic Policy 1 and 2, laid down by the Republic of the Union of Myanmar)
Activity No. | Category of Activity | Activities | Implementing Agency | Category of Expense | Outputs | KPI | TOTAL BUDGET to Dec 2019 | 2017 | Q-1'18 | Q-2'18 | Q-3'18 | Q-4'18 | 2018 Total | Q 1'19 | Q -2,19 | Q3'19 | Q4'19 | 2019 Total | Additional expenses for contracts to be signed in 2019
[8 empty] | Actual | Actual | Actual | Actual | Budget | Budget | Budget | Budget | Budget | Budget | Budget
Objective 1: To acquire & disseminate accurate, correct and up-to-date information regarding the management of natural resources and associated material revenues in a timely manner and to make the information publicly available
1.1 | Communication and Outreach
1.1.1 | MEITI Report Launch | Report Print | NCS Communication, Communication and Outreach Sub-Committee | Goods | Printed copies of report (Executive Summary, Full Report, Myanmar Version, English Version) | No. of copies of each version printed No. of copies of each version distriubuted | 42278.557 | 0 | 0 | 0 | 12278.557 | 15000 | 27278.557 |  | 15000 |  |  | 15000
1.1.2 | Forestry Report Launch | Report Print | NCS Communication, Communication and Outreach Sub-Committee | Goods | Printed copy of Forestry Report (Myanmar and English version) | No. of copies of each version printed No. of copies of each version distriubuted | 15000 | 0 | 0 | 0 | 0 | 15000 | 15000 |  |  |  |  | 0
1.1.3 | MEITI Report Launch (Including Dinner) | Media including TV, Radio, events and activities includign press release | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased knowledge of EITI and extractives in Myanmar | No. of events, TV /Radio Programs/ Media Articles No. and details of participants and audiences (gender, geographical location, ethnicity etc) Event Reports / quaility (accuracy of media reports) | 51980.9173 | 0 | 0 | 0 | 1980.9173 | 30000 | 31980.9173 |  | 10000 | 10000 |  | 20000
1.1.4 | Forestry Report Launch | Media including TV, Radio, events and activities includign press release | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased knowledge of Forestry extractives in Myanmar | No. of events, TV /Radio Programs/ Media Articles No. and details of participants and audiences (gender, geographical location, ethnicity etc) Event Reports / quaility (accuracy of media reports) | 15000 | 0 | 0 | 0 | 0 | 9000 | 9000 |  |  | 6000 |  | 6000
1.1.5 | Public Debates | Public Gathering/Debate and Road Show | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased knowledge of EITI and extractives in Myanmar | No. of public gatherings, debates, roadshow events No. and details of participants Event Feedback and Reports | 40000 | 0 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 10000 | 10000 |  | 30000
1.1.6 | Prints and Publication | Other prints and IEC material development | NCS Communication, Communication and Outreach Sub-Committee | Goods | IEC Materials | No and type of materials produced No and type of materails distributed/ viewed online Feedback on materials (?) | 30388.6153 | 0 | 2704.6243 | 2683.991 | 0 | 10000 | 15388.6153 |  | 10000 | 5000 |  | 15000
1.1.7a. | Website | Redesign, regular update and maintenance MEITI Website & on-line library | NCS Communication, Communication and Outreach Sub-Committee | Non Consulting Services | Website | No. of hits on website Feedback Survey Validation Comments | 5496.8921 | 575.4544 | 1279.1217 | 0 | 2642.3161 |  | 3921.4377 |  | 1000 | 0 | 0 | 1000
1.1.7b. | Video Production and Broadcasting | Video Production and Broadcasting | NCS Communication, Communication and Outreach Sub-Committee | Non Consulting Services | Videos | Number of views, boradcasts, feedback | 15000 | 0 | 0 | 0 | 0 |  | 0 | 15000 |  |  |  | 15000
1.1.8 | Web-portal and Infographic | Open data, Inforgraphic and updated data | NCS Communication, Communication and Outreach Sub-Committee | Non Consulting/ Consulting | Infographics and open data pages | No. of users Feedback and Validation Comments | 10000 | 0 | 0 | 0 | 0 | 6000 | 6000 |  | 4000 |  |  | 4000
1.1.10 | National EITI Conference | National EITI Conference | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased understanding of MEITI Improved multistakeholder participation Documented assessment of progress, Input for planning | Event Report No. and details of participants Progress assessment and Planning input Feedback from participants | 15000 | 0 | 0 | 0 | 0 |  | 0 | 15000 |  |  |  | 15000
Sub Total 1 | [6 empty] | 240144.9816 | 575.4544 | 3983.7459 | 2683.991 | 16901.7903 | 95000 | 118569.5272 | 40000 | 50000 | 31000 | 0 | 121000
Objective 2: To create an enabling environment for the effective implementation of the EITI Standard
2.1 | HR, Operation and Office Administration
2.1.1 | MOBD Operational Cost | MOBD Staff travel and Office Supplies | MOBD | Operating Cost/ Goods | Project Financial Management, Procurement and Grant Compliance | FM reports to MSG and Donors, Procurement Plans and Documentation OAG Audit LC and WC Support to EITI process | 52712.6091 | 4616.3484 | 5225.29 | 2274.8332 | 3096.1375 | 7500 | 18096.2607 | 7500 | 7500 | 7500 | 7500 | 30000
2.1.2 | NCS Operation Cost -Salaries | NCS Staff Salaries | NCS | Operating Cost | Successful Implementation of Work Plan activities | APR EITI Reconciliation Reports MSG and Subcommittee Minutes Staff Performance Evaluations | 482816.4517 | 43920.6314 | 65176.2842 | 12867.912 | 72101.624 | 57750 | 207895.8203 | 57750 | 57750 | 57750 | 57750 | 231000
2.1.3a | NCS Operation Cost | NCS Overheads ( Utilities, Travel, Communication service, Maintenance, Stationary, consumable material and other miscellaneous) | NCS | Operating Cost | Successful Implementation of Work Plan activities | APR EITI Reconciliation Reports MSG and Subcommittee Minutes | 93952.9489 | 10438.0187 | 21284.5961 |  | 17230.3341 | 9000 | 47514.9302 | 9000 | 9000 | 9000 | 9000 | 36000
2.1.3b. | Consultant support service | Additional Travel and Accommodation costs to support consultants (BO, Cadastre etc) | NCS | Operating Cost | Facilitation of Consultants' Work | Consultant Deliverables | 23277.3194 | 0 | 0 | 0 | 777.3194 | 4500 | 5277.3194 | 4500 | 4500 | 4500 | 4500 | 18000
2.1.4 | NCS Operation Cost - Rent | NCS Office Rental | NCS | Operating Cost | Office Space | Office Rental Contract and Payment Reciept | 65782.2924 | 9031.9439 | 12349.4486 | 0 | 36000.9 |  | 48350.3486 |  |  | 8400 |  | 8400 | 25000
2.1.5 | Office Set Up Cost | Equipment and Furniture | NCS, MOBD | Goods | Furniture and Equipment | Purchase Receipts Procurement Report Inventory | 41380.4894 | 9958.6036 | 6831.8858 | 0 | 0 | 24590 | 31421.8858 |  |  | 0 | 0 | 0
2.1.6 | Fund raising | Secure alternative funding from development partners | MSG, NCS | Workshop and Meeting | Funds raised | Meeting Minutes Workshop Reports Funds Raised | 1000 | 0 | 0 | 0 | 0 | 1000 | 1000 |  |  |  |  | 0
2.1.7 | Fund raising- Advocacy | Secure increased government contribution to EITI | MOBD, MSG | Non Consulting |  |  | 3000 | 0 | 0 | 0 | 0 | 2000 | 2000 | 1000 |  |  |  | 1000
2.1.8 | MSG Meeting | MSG Meeting | NCS | Workshop and Meeting | MSG Meeting Decisions and Outputs (approved TOR, reports etc) | Meeting Minutes Approved (Myanmar and English) Minutes posted on MEITI Website Funds Raised | 86576.5786 | 8192.0498 | 23326.0527 | 2990.5236 | 7067.9524 | 9000 | 42384.5287 | 9000 | 9000 | 9000 | 9000 | 36000
2.1.9 | Sub-committee Meeting | MSG Sub-Committee Meetings | NCS | Workshop and Meeting | Subcommittee Meeting Recommendations and Outputs (draft TOR, reports etc) | Meeting Minutes Approved (Myanmar and English)Minutes posted on MEITI Website Funds Raised | 29437.7634 | 3767.6924 | 2866.3571 | 2905.379 | 2398.335 | 3500 | 11670.0711 | 3500 | 3500 | 3500 | 3500 | 14000
2.1.10 | Translation Fee for related documents | [5 empty] | 20000 | 0 | 0 | 0 | 0 | 5000 | 5000 | 4000 | 3500 | 3500 | 4000 | 15000
Sub Total 2.1 | [6 empty] | 899936.4529 | 89925.2881 | 137059.9144 | 21038.6479 | 138672.6025 | 123840 | 420611.1648 | 96250 | 94750 | 103150 | 95250 | 389400
2.2 | Workplan and Governance (APR, M&E- Review workshops)
2.2.1 | M&E | Review of annual progress (workplan), produce annual activity/progress report. | NCS, MSG | Workshop and Meeting | Increased understanding of MEITI Improved multistakeholder participation Documented assessment of progress, Input for planning | Event Report No. and details of participants Progress assessment and Planning input Feedback from participants | 6000 | 0 | 0 | 0 | 0 |  | 0 |  | 6000 |  |  | 6000
2.2.4 | Implementation of EITI report Recommendations Workshop | Workshop to develop the workplan for implementation of EITI recommendations | MOBD, NCS, Subcommittee, MSG | Workshop and meeting | Systematic assessment of EITI Recommendations from reports and planning for their implementation | SMART Work Plan for implementation Recommendations | 8444.3111 | 0 | 0 | 0 | 2444.3111 | 0 | 2444.3111 | 6000 |  |  |  | 6000
2.2.5 | Implementation of EITI report Recommendations Workplan | Implement the workplan for EITI recommendations | NCS, MSG, Government Agencies | Workshop and meeting/ Consultancy/ Goods | Outputs according to the agreed work plan | Indicators according to the agreed work plan | 50000 | 0 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 40000
2.2.6 | SOE Reform Workshop | Two-day workshop on SOE situations and future reform plans for extractor sector | MOBD, NCS, Subcommittee, MSG | Workshop and Meeting | Increased awareness of MEITI Report recommendtions on SOE Reform Documented multi-stakeholder review of current SOE reform plans, achievements and challenges Plans for ongoing reforms and their coordination with MEITI | Workshop Report incl participation Documentation of assessments, decisions and plans | 50000 | 0 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 40000
2.2.7 | Validation | Data Collection and Stakeholder Consultation workshops for initial assessment | NCS, MSG | Workshop and meeting | Multistakeholder assessment and documentation of MEITI process Capacity Building for MEITI Stakeholders | Validation Report | 8757.9419 | 0 | 0 | 0 | 2957.9419 | 5800 | 8757.9419 |  |  |  |  | 0
2.2.8 | Validation | Contribution to International Secretariat | MOBD, NCS |  | Payment made | Money transfer receipt, Bank Transaction Sheet, letter of acknowledgement from EITI | 10000 | 0 | 0 | 0 | 0 | 10000 | 10000 |  |  |  |  | 0
Sub Total 2.2 | [6 empty] | 133202.2531 | 0 | 0 | 0 | 5402.2531 | 35800 | 41202.2531 | 26000 | 26000 | 20000 | 20000 | 92000
2.3 | Sub-National Coordination Unit (Formation and Functioning)
2.3.1 | SNU Formation and Coordination | Establishing Sub-National Coordination Units at State and Division level and further coordination with Union EITI. | NCS, MSG, Communication Officer | Workshop and meeting | SNUs Formed (Membership, TOR) Meeting Records / Minutes/ Reports | No. of SNUs Formed SNU Membership details (inclusivity, participation, geographic coverage) SNU TORs and Work Plans | 80057.6481 | 0 | 19508.4581 | 0 | 10549.19 | 10000 | 40057.6481 | 10000 | 10000 | 10000 | 10000 | 40000
2.3.2 | SNU Meetings / Workshops | Supporting regular meetings /workshops | MOBD, NCS, MSG, SNUs | Workshop and meeting | SNU Meetings Held Meeting Minutes SNU activities conducted (according to Workplan?) | No. of meetings Participation, Gender, Geogrpahic Coverage etc Indicators according to SNU Objectives and activities | 38000 | 0 | 0 | 0 | 0 | 8000 | 8000 | 6500 | 6500 | 6500 | 10500 | 30000
2.3.3 | Coordination between MSG and SNUs | Review and evaluate reports from SNUs and determine coordinate consistent response to issues raised. MSG to establish internal monitoring and evaluation mechanism on workplan implementation?? | NCS, MSG, SNU |  | ??? | ??? | 25000 | 0 | 0 | 0 | 0 | 3000 | 3000 | 4000 | 5000 | 6000 | 7000 | 22000
Sub Total 2.3 | [6 empty] | 143057.6481 | 0 | 19508.4581 | 0 | 10549.19 | 21000 | 51057.6481 | 20500 | 21500 | 22500 | 27500 | 92000
Sub Total 2 |  |  |  | Sub Total 2 |  |  | 1176196.354 | 89925.2881 | 156568.3726 | 21038.6479 | 154624.0455 | 180640 | 512871.0659 | 142750 | 142250 | 145650 | 142750 | 573400
Objective 3:To support implementation of sustainable development and natural resource governance reforms through the successful execution of EITI.
3.1 | Technical and Reporting (IA main report, Forestry, BO, Mining Cadaster, SOE, Review of Artisenal Mining, Fasibility studies, Sub-national study, Implementation of recommendations, & other technical studies)
3.1.1 | Legislative institutionalization | Research to recommend legal options to EITI institunalization. | NCS, Subcommittee, MSG | Consultancy | Research Report and Recommendations | Research Report and Recommendations accpeted by MSG | 25000 | 0 | 0 | 0 | 0 |  | 0 | 10000 | 15000 |  |  | 25000
3.1.2 | Legislative institutionalization | Developing a draft EITI Law or amemdments to Sectoral Laws | NCS, Subcommittee, MSG | Consultancy | Recommendations from above report implemented | Indicators related to each recommendation | 20000 | 0 | 0 | 0 | 0 |  | 0 |  | 5000 | 15000 |  | 20000
3.1.3 a | EITI Reconciliation Report | Independent Administrator and procure firm each year for the annual report (including scoping study) | MOBD, NCS, IA | Consulting | EITI Reconciliation Reports | Reports produced by deadline Reports approved by MSG Validation results on EITI Standard 2-6 | 636850 | 110740 | 83055 | 0 | 0 | 161055 | 244110 | 78000 | 104000 | 100000 |  | 282000 | 150000
3.1.3 b | EITI Reconciliation Report | Report reconciliation and Reporting entities workshops-Main IA |  |  |  |  | 48138.0885 | 4439.4513 | 13698.6372 | 0 | 0 | 15000 | 28698.6372 |  |  |  | 15000 | 15000
3.1.4 a | Forestry Reconciliation Report | IA - First report |  | Consulting | Forestry Reconconciliation Report(s) | Report(s) approved by MSG | 320000 | 0 | 48000 | 80000 | 0 | 32000 | 160000 |  | 64000 |  | 96000 | 160000
3.1.4 b | Forestry Reconciliation Report | Reporting entities workshops-Forestry IA |  |  |  |  | 8952.4048 | 0 | 3952.4048 | 0 | 0 |  | 3952.4048 |  |  | 5000 |  | 5000
3.1.4 c | Hydro Reconcillation Report | Independent Administrator and procure firm each year for the annual report (including scoping study) |  |  |  |  | 160000 | [7 empty] | 64000 |  | 96000 | 160000
3.1.5 | Mineral and Gemstone Cadaster | Design Phase | MONREC, NCS, Subcommitte, MSG | Consulting | Preliminary, Intermediate and Final Report Mineral Cadastre Conceptual Design TOR for Phase 2 | Documents received and approved by MONREC and MSG | 119125.15 | 40017 | 40024 | 0 | 39084.15 |  | 79108.15 |  |  |  |  | 0
3.1.6 a | Mineral and Gemstone Cadaster | Pre-cadaster Working Group Consultant | MONREC, NCS, Subcommitte, MSG | Consulting | Training and on the job support Precadastre developed | No. of staff trained No. of Training Hours completed Completeness of Precadastre | 31500 | 0 | 0 | 0 | 12600 |  | 12600 | 18900 |  |  |  | 18900
3.1.6 b | Office Set Up Equipment for Pre Cadaster Working | [5 empty] | 23000 | 0 | 0 | 0 | 0 | 23000 | 23000 |  |  |  |  | 0
3.1.6 c | Office Set up-Furniture for Pre-Cadastre working group | [5 empty] | 10000 | 0 | 0 | 0 | 0 | 10000 | 10000 |  |  |  |  | 0
3.1.6 d | ARC,GIS Software | [5 empty] | 7200 | 0 | 0 | 0 | 0 | 7200 | 7200 |  |  |  |  | 0
3.1.6 e | Maps, Stationery | [5 empty] | 5000 | 0 | 0 | 0 | 0 | 5000 | 5000 |  |  |  |  | 0
3.1.7 | Mineral and Gemstone Cadaster | Development and installation of cadaster. | MONREC, NCS, Subcommitte, MSG | Consulting | Deliverables outlined in TOR for Phase 2 | Indicators according to deliverables from TOR Phase 2 | 216000 | 0 | 0 | 0 | 0 |  | 0 |  | 72000 |  | 144000 | 216000 | 504000
3.1.8 | Mineral and Gemstone Cadaster | Purchase of IT equipment and furniture | MONREC, NCS, MOBD | Goods | Equipment and Furniture | Procurement report Purchase Receipt Inventory | 80000 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 80000 | 80000
3.1.9 | Research Study | Study of Artisanal and small scale mining (including Illegal mining) | IA, NCS, Subcommittee, MSG | Consulting | Research Report and Recommendations | Report approved by MSG | 30000 | 0 | 0 | 0 | 0 |  | 0 |  | 15000 | 15000 |  | 30000
3.1.10 | Research Study | EITI related research according to MSG including Feasibility Study (Hydro/ Fishery, etc) | NCS, Subcommittee, MSG | Consulting | Research Report and Recommendations | Report approved by MSG |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  | 0
3.1.11a. | Beneficial Ownership | Development of Workplan, Communicaiton Plan, Capacity Building Plan and Pilot Project | NCS, Subcommittee, MSG | Consultancy | BO Work Plan, BO Communications Plan, BO Capacity Development Plan, BO Pilot Project | Deliverables approved by MSG | 120000 | 0 | 36000 | 0 | 0 | 84000 | 120000 |  |  |  |  | 0
3.1.11b. | Beneficial Ownership | Domestic Consultant | NCS, Subcommittee, MSG | Consultancy |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0
3.1.12 | Beneficial Ownership Meetings | BO workshops and Taskforce Meetings | NCS, Task Force | Meeting and Workshop |  | No. of workshop/ meeting | 35588.5453 | 0 | 0 | 3587.4953 | 2001.05 | 6000 | 11588.5453 | 6000 | 6000 | 6000 | 6000 | 24000
3.1.13 | Beneficial Ownership | [5 empty] | 50000 | [6 empty] | 50000 |  |  |  | 50000
Sub Total 3.1 | [6 empty] | 1946354.1886 | 155196.4513 | 224730.042 | 83587.4953 | 53685.2 | 343255 | 705257.7373 | 162900 | 345000 | 141000 | 437000 | 1085900
3.2 | Training and Capacity Development (Capacity Development for 3 MSG entities, MOBD, NCS & SNU capacity building)
3.2.1 | Capacity Development | Implement Capacicty Development Plan (MSG, Private Sector, Governemnt, CSO, Media, EAOs, MOBD, NCS, Parliament and others) | NCS, MSG | Meeting and Workshop | Outputs defined in capacity development plan | Indicators defined in Capacity Development Plan Incld No. of participants, participant criteria (gender, stakeholder group, geographic location etc) Participant feedback | 55085.9759 | 8267.6968 | 4147.6666 | 706.3134 | 11964.2991 | 10000 | 26818.2791 | 10000 | 10000 |  |  | 20000
3.2.3 | Capacity Development- Study Tour | MSG Study Tours | MSG | Non Consulting | Outputs defined in Study Tour Concept Note or Plan | Indicators from concpet note or plan Incld No. of participants, participant criteria (gender, stakeholder group, geographic location etc) Participant feedback and cascading activities | 36807.7365 | 0 | 0 | 0 | 12702.7365 | 13000 | 25702.7365 | 11105 |  |  | 0 | 11105
3.2.4 | Capacity Development- EITI events | EITI Global/ Regional Conferences and Board Meetings | MSG | Non Consulting | EITI Internnational Events attended | No. of events attended, No. of participants, cascade activities | 15000 | 0 | 0 | 0 | 0 |  | 0 | 15000 |  | 0 |  | 15000
3.2.5 | Financial Management Training (MOBD/NCS) | MOBD Financial management capacity development | NCS, Subcommittee, MSG | Consulting | Training and on the job support | No. of MOBD staff trained | 30410.5924 | 0 | 5969.7164 | 0 | 9440.876 |  | 15410.5924 | 7500 |  | 7500 |  | 15000
Sub Total 3.2 | [6 empty] | 137304.3048 | 8267.6968 | 10117.383 | 706.3134 | 34107.9116 | 23000 | 67931.608 | 43605 | 10000 | 7500 | 0 | 61105
Sub Total 3 |  |  |  | Sub Total 3 |  |  | 2083658.4935 | 163464.1481 | 234847.425 | 84293.8087 | 87793.1116 | 366255 | 773189.3454 | 206505 | 355000 | 148500 | 437000 | 1147005
GRAND TOTAL |  |  |  | Grand Total |  |  | 3499999.829 | 253964.8905 | 395399.5435 | 108016.4475 | 259318.9475 | 641895 | 1404629.9385 | 389255 | 547250 | 325150 | 579750 | 1841405
Projected Budget % against total grant | [7 empty] | 7.256% | 11.3% | 3.086% | 7.409% | 18.34% | 40.13% | 11.12% | 15.64% | 9.29% | 16.56% | 52.61%
Cumulative % | [7 empty] | 7.256% | 18.55% | 21.64% | 29.05% | 47.39% | 47.39% | 58.51% | 74.15% | 83.44% | 100% | 100%
Objective 3 (Capacity Building)
Disbursement Category 3 | [6 empty] | 683932.1824

## Workplan 13-5-20
MYANMAR EITI PROJECT PHASE II
2017-2021 WORK PLAN & BUDGET
Strategic Goals: To promote transparency and accountability in the extractive industries and material revenue management of the Union of Myanmar. (in line with the National Economic Policy 1 and 2, laid down by the Republic of the Union of Myanmar)
Activity No. | Category of Activity | Activities | Implementing Agency | Category of Expense | Outputs | KPI | TOTAL BUDGET WB 3.5 MUSD Grant | 2017 | Q-1'18 | Q-2'18 | Q-3'18 | Q-4'2018 | 2018 Total | Q -1,19 | Q -2,19 | July & August 2019 | Sept'19 | Q -3,19 | Oct'19 | Nov'19 | Dec'19 | Q -4,19 | 2019 Total | Jan'2020 | Feb'2020 | Mar'2020 | Q -1,2020 | Apr'2020 | 13th May' 2020 | Up to 13 May 2020 | Budget for 3.5 Million USD Remainder (13-5-20) | Budget for 3.5 Million USD Remainder W&G Sub-Committee (13,14-2-2020) | Budget for 3.5 Million USD Remainder | Budget for 3.5 Million USD Remainder | Q4'19 | Q -1,20 | Q -2,20 | Q3'20 | Q4'20 | Q -1,21 | Up to 2021 March
[8 empty] | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Balance | Balance | Budget | Budget | Budget | Budget | Budget | Budget | Budget | Budget | Budget
1.1 | Communication and Outreach
1.1.1 | MEITI Report Print | Report Print |  | Goods | Printed copies of report (Executive Summary, Full Report, Myanmar Version, English Version) | No. of copies of each version printed No. of copies of each version distriubuted | 22928.557 | 0 | 0 | 0 | 12278.557 | 0 | 12278.557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 12278.557 | 10650 | 10650 | 10650 | 10650 |  | 10650 |  |  |  |  | 10650
1.1.2 | Forestry Report Printing | Report Print | NCS Communication, Communication and Outreach Sub-Committee | Goods | Printed copy of Forestry Report (Myanmar and English version) | No. of copies of each version printed No. of copies of each version distriubuted | 7941 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7941 | 7941 |  |  |  | 0 | 7941 | 0 | 0 |  | 0 |  |  | 7941 | 0 | [9 empty] | 0
1.1.3 | MEITI Report Launch Events etc | Media including TV, Radio, events and activities includign press release | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased knowledge of EITI and extractives in Myanmar | No. of events, TV /Radio Programs/ Media Articles No. and details of participants and audiences (gender, geographical location, ethnicity etc) Event Reports / quaility (accuracy of media reports) | 28592.5841 | 0 | 0 | 0 | 1980.9173 | 123.6668 | 2104.5841 | 19387 | 2101 |  |  | 0 |  |  |  | 0 | 21488 | 0 | 0 |  | 0 |  |  | 23592.5841 | 5000 | 5000 | 5000 | 5000 |  | 2500 | 2500 |  |  |  | 5000
1.1.4 | Forestry Report Launch Events etc | Media including TV, Radio, events and activities includign press release | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased knowledge of Forestry extractives in Myanmar | No. of events, TV /Radio Programs/ Media Articles No. and details of participants and audiences (gender, geographical location, ethnicity etc) Event Reports / quaility (accuracy of media reports) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
1.1.5 | Public Debates | Public Gathering/Debate and Road Show | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased knowledge of EITI and extractives in Myanmar | No. of public gatherings, debates, roadshow events No. and details of participants Event Feedback and Reports | 6815.1016 | 0 | 0 | 0 | 0 | 4062.1016 | 4062.1016 | 2753 |  |  |  | 0 |  |  |  | 0 | 2753 | 0 | 0 |  | 0 |  |  | 6815.1016 | 0 | [9 empty] | 0
1.1.6 | Prints and Publication | Other prints and IEC material development | NCS Communication, Communication and Outreach Sub-Committee | Goods | IEC Materials | No and type of materials produced No and type of materails distributed/ viewed online Feedback on materials (?) | 18866.3617 | 0 | 2706.2626 | 2736.0684 | 0 | 1230.0308 | 6672.3617 |  | 4964 | 1630 |  | 1630 |  |  |  | 0 | 6594 | 0 | 0 | 1538.9125 | 1538.9125 |  |  | 14805.2742 | 4061.0875 | 5600 | 5600 | 5600 |  | 5600 |  |  |  |  | 5600
1.1.7a. | Website | Redesign, regular update and maintenance MEITI Website & on-line library | NCS Communication, Communication and Outreach Sub-Committee | Non Consulting Services | Website | No. of hits on website Feedback Survey Validation Comments | 5097.565 | 575.4544 | 1279.7946 | 0 | 2642.3161 |  | 3922.1106 |  |  |  |  | 0 | 442 |  |  | 442 | 442 | 0 | 9 |  | 9 |  |  | 4948.565 | 149 | 149 |  |  |  | 158 |  |  |  |  | 158
1.1.7b. | Video Production and Broadcasting | Video Production and Broadcasting | NCS Communication, Communication and Outreach Sub-Committee | Non Consulting Services | Videos | Number of views, boradcasts, feedback | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
1.1.8 | Web-portal and Infographic | Open data, Inforgraphic and updated data | NCS Communication, Communication and Outreach Sub-Committee | Non Consulting/ Consulting | Infographics and open data pages | No. of users Feedback and Validation Comments | 3000 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 3000 | 3000 | 3000 |  |  | 3000 |  |  |  |  | 3000
1.1.10 | National EITI Conference | National EITI Conference | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased understanding of MEITI Improved multistakeholder participation Documented assessment of progress, Input for planning | Event Report No. and details of participants Progress assessment and Planning input Feedback from participants | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
Sub Total 1 | [6 empty] | 93241.1694 | 575.4544 | 3986.0572 | 2736.0684 | 16901.7903 | 5415.7991 | 29039.715 | 22140 | 7065 | 1630 | 7941 | 9571 | 442 | 0 | 0 | 442 | 39218 | 0 | 9 | 1538.9125 | 1547.9125 | 0 | 0 | 70381.0819 | 22860.0875 | 24399 | 24250 | 21250 | 0 | 21908 | 2500 | 0 | 0 | 0 | 24408
Objective 2: To create an enabling environment for the effective implementation of the EITI Standard
2.1 | HR, Operation and Office Administration
2.1.1 | MOBD Operational Cost | MOBD Staff travel and Office Supplies | MOBD | Operating Cost/ Goods | Project Financial Management, Procurement and Grant Compliance | FM reports to MSG and Donors, Procurement Plans and Documentation OAG Audit LC and WC Support to EITI process | 114623 | 2101 | 1543 | 1253 | 2683 | 1709 | 7188 | 1825 | 2342 | 1081.21 | 947 | 2028.21 | 469 | 320 | 790 | 1579 | 7774.21 | 708 | 655 | 1036.2241 | 2399.2241 | 196.5997 | 415.573 | 20074.6069 | 94548.3931 | 96204 | 96859 | 96859 |  | 3000 | 3000 | 3000 | 22300 | 65559 | 96859
2.1.2 | NCS Operation Cost -Salaries | NCS Staff Salaries | NCS | Operating Cost | Successful Implementation of Work Plan activities | APR EITI Reconciliation Reports MSG and Subcommittee Minutes Staff Performance Evaluations | 589182.106 | 43920.6314 | 65176.2842 | 13117.5879 | 71704.6044 | 13651.818 | 163650.2945 | 52516 | 34762 | 40605.18 | 26566 | 67171.18 |  | 15409 |  | 15409 | 169858.18 | 28386 | 15191 | 14858.737 | 58435.737 | 28811.2022 |  | 464676.0452 | 124506.0607 | 168176 | 168116 | 168116 |  | 42000 | 60000 | 66116 |  |  | 168116
2.1.3a | NCS Operation Cost | NCS Overheads ( Utilities, Travel, Communication service, Maintenance, Stationary, consumable material and other miscellaneous) | NCS | Operating Cost | Successful Implementation of Work Plan activities | APR EITI Reconciliation Reports MSG and Subcommittee Minutes | 136625.3707 | 10438.0187 | 21284.5961 | 0 | 17263.446 | 0 | 38548.0421 | 14988 | 7041 | 7076.04 | 7238 | 14314.04 |  | 5213 |  | 5213 | 41556.04 | 5668 | 2239.27 | 1061.5865 | 8968.8565 | 386.5302 |  | 99897.4874 | 36727.8833 | 38176 | 38658 | 38658 |  | 8475 | 12000 | 18183 |  |  | 38658
2.1.3b. | Consultant support service | Additional Travel and Accommodation costs to support consultants (BO, Cadastre etc) | NCS | Operating Cost | Facilitation of Consultants' Work | Consultant Deliverables | 3215.3194 | 0 | 0 | 0 | 777.3194 | 0 | 777.3194 |  | 1650 |  | 788 | 788 |  |  |  | 0 | 2438 | 0 | 0 |  | 0 |  |  | 3215.3194 | 0 | [9 empty] | 0
2.1.4 | NCS Operation Cost - Rent | NCS Office Rental | NCS | Operating Cost | Office Space | Office Rental Contract and Payment Reciept | 88193.1054 | 9031.9439 | 12382.2615 | 0 | 36000.9 | 0 | 48383.1616 |  |  |  | 30778 | 30778 |  |  |  | 0 | 30778 | 0 | 0 |  | 0 |  |  | 88193.1054 | 0 |  |  | 0 | [6 empty] | 0
2.1.5 | Office Set Up Cost | Equipment and Furniture | NCS, MOBD | Goods | Furniture and Equipment | Purchase Receipts Procurement Report Inventory | 32492.7881 | 9958.6036 | 4526.1845 | 0 | 0 | 0 | 4526.1845 |  |  |  | 17677 | 17677 | 324 |  |  | 324 | 18001 | 0 | 7 |  | 7 |  |  | 32492.7881 | 0 | 0 |  | 0 | 0 | [5 empty] | 0
2.1.6 | Fund raising- Advocacy | Secure increased government contribution to EITI | MOBD, MSG | Non Consulting |  |  | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
2.1.7 | MSG Meeting | MSG Meeting | NCS | Workshop and Meeting | MSG Meeting Decisions and Outputs (approved TOR, reports etc) | Meeting Minutes Approved (Myanmar and English) Minutes posted on MEITI Website Funds Raised | 78709.2271 | 8192.0498 | 23326.0527 | 3048.5487 | 7020 | 3807.5759 | 37202.1773 | 6602 | 3376 | 6105 | 3598 | 9703 |  |  |  | 0 | 19681 | 7134 | 0 | 3636.7787 | 10770.7787 |  |  | 75846.0058 | 2863.2213 | 6500 | 6500 | 6500 |  |  | 6500 |  |  |  | 6500
2.1.8 | Sub-committee Meeting | MSG Sub-Committee Meetings | NCS | Workshop and Meeting | Subcommittee Meeting Recommendations and Outputs (draft TOR, reports etc) | Meeting Minutes Approved (Myanmar and English)Minutes posted on MEITI Website Funds Raised | 24609.6681 | 3767.6924 | 2866.3571 | 2961.752 | 2398.335 | 2794.5316 | 11020.9757 | 2233 | 3108 | 732 | 713 | 1445 | 133 |  | 200 | 333 | 7119 | 0 | 218 | 979.5944 | 1197.5944 |  |  | 23105.2625 | 1504.4056 | 2484 | 2702 | 2702 |  | 1400 | 1302 |  |  |  | 2702
2.1.8 a | Work Plan Review Workshop | [5 empty] | 2400 | [9 empty] | 2400 | 2400 |  |  |  | 0 | 2400 | 0 | 0 |  | 0 |  |  | 2400 | 0 | [9 empty] | 0
2.1.8 b | EITI Awareness Meeting | [5 empty] | 537 | [9 empty] | 537 | 537 |  |  |  | 0 | 537 | 0 | 0 |  | 0 |  |  | 537 | 0 | [9 empty] | 0
2.1.9 | Translation Fee for related documents | [5 empty] | 15493 | 2515 | 3691 | 1066 | 461 | 0 | 5218 | 3603 | 810 | 232 |  | 232 | 3115 |  |  | 3115 | 7760 | 0 | 0 |  | 0 |  |  | 15493 | 0 | [9 empty] | 0
Sub Total 2.1 | [6 empty] | 1086080.5849 | 89924.9397 | 134795.7361 | 21446.8887 | 138308.6048 | 21962.9256 | 316514.1552 | 81767 | 53089 | 55831.43 | 91242 | 147073.43 | 4041 | 20942 | 990 | 25973 | 307902.43 | 41896 | 18310.27 | 21572.9208 | 81779.1908 | 29394.3321 | 415.573 | 825930.6207 | 260149.9641 | 311540 | 312835 | 312835 | 0 | 54875 | 82802 | 87299 | 22300 | 65559 | 312835
2.2 | Workplan and Governance (APR, M&E- Review workshops)
2.2.1 | M&E Workshop | Review of annual progress (workplan), produce annual activity/progress report. | NCS, MSG | Workshop and Meeting | Increased understanding of MEITI Improved multistakeholder participation Documented assessment of progress, Input for planning | Event Report No. and details of participants Progress assessment and Planning input Feedback from participants | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
2.2.4 | Implementation of EITI report Recommendations Workshop | Workshop to develop the workplan for implementation of EITI recommendations | MOBD, NCS, Subcommittee, MSG | Workshop and meeting | Systematic assessment of EITI Recommendations from reports and planning for their implementation | SMART Work Plan for implementation Recommendations | 2444.3111 | 0 | 0 | 0 | 2444.3111 | 0 | 2444.3111 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 2444.3111 | 0 | [9 empty] | 0
2.2.5 | MSG Governance Review Workshop | MSG Reform and Selection | NCS, MSG, Government Agencies | Workshop and meeting/ Consultancy/ Goods | Outputs according to the agreed work plan | Indicators according to the agreed work plan | 5238 | 0 | 3224 | 0 | 0 | 0 | 3224 |  | 2014 |  |  | 0 |  |  |  | 0 | 2014 | 0 | 0 |  | 0 |  |  | 5238 | 0 | [9 empty] | 0
2.2.5 a | EITI Restructure Review | Implementation of EITI restructuring | MOBD, NCS, Subcommittee, MSG, Government Agencies | Workshop and meeting/ Consultancy/ Goods |  |  | 0 | [10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
2.2.6 | SOE Reform Workshop | SOE workshop, Pre-meeting on SOE situations and future reform plans for extractor sector | MOBD, NCS, Subcommittee, MSG | Workshop and Meeting | Increased awareness of MEITI Report recommendtions on SOE Reform Documented multi-stakeholder review of current SOE reform plans, achievements and challenges Plans for ongoing reforms and their coordination with MEITI | Workshop Report incl participation Documentation of assessments, decisions and plans | 12115 | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 5456 |  | 1222 | 1222 |  | 1284 |  | 1284 | 8232 | 0 | 0 |  | 0 |  |  | 8232 | 3883 | 3883 | 3883 | 3883 |  |  | 3883 |  |  |  | 3883
2.2.7 | Validation | Data Collection and Stakeholder Consultation workshops for initial assessment /Validation Group Meeting and Consultation Meeting for 12 Correction Action | NCS, MSG | Workshop and meeting | Multistakeholder assessment and documentation of MEITI process Capacity Building for MEITI Stakeholders | Validation Report | 9487.9419 | 0 | 0 | 0 | 2957.9419 | 0 | 2957.9419 | 2330 |  |  |  | 0 |  |  |  | 0 | 2330 | 0 | 0 |  | 0 |  |  | 5287.9419 | 4200 | 4200 | 4200 | 4200 |  | 1050 | 1050 | 1050 | 1050 |  | 4200
2.2.8 | Validation | Contribution to International Secretariat | MOBD, NCS |  | Payment made | Money transfer receipt, Bank Transaction Sheet, letter of acknowledgement from EITI | 10000 | 0 | 0 | 0 | 0 | 10000 | 10000 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 10000 | 0 | [9 empty] | 0
Sub Total 2.2 | [6 empty] | 39285.2531 | 0 | 3224 | 0 | 5402.2531 | 10000 | 18626.2531 | 2600 | 7470 | 0 | 1222 | 1222 | 0 | 1284 | 0 | 1284 | 12576 | 0 | 0 | 0 | 0 | 0 | 0 | 31202.2531 | 8083 | 8083 | 8083 | 8083 | 0 | 1050 | 4933 | 1050 | 1050 | 0 | 8083
2.3 | Sub-National Coordination Unit (Formation and Functioning)
2.3.1 | SNU Formation and Coordination | Establishing Sub-National Coordination Units at State and Division level and further coordination with Union EITI. | NCS, MSG, Communication Officer | Workshop and meeting | SNUs Formed (Membership, TOR) Meeting Records / Minutes/ Reports | No. of SNUs Formed SNU Membership details (inclusivity, participation, geographic coverage) SNU TORs and Work Plans | 34749.2633 | 0 | 10632.5588 | 0 | 10549.19 | 3180.5145 | 24362.2633 | 10387 |  |  |  | 0 |  |  |  | 0 | 10387 | 0 | 0 |  | 0 |  |  | 34749.2633 | 0 | [9 empty] | 0
2.3.2 | Coordination between MSG and SNUs | Review and evaluate reports from SNUs and determine coordinate consistent response to issues raised. MSG to establish internal monitoring and evaluation mechanism on workplan implementation?? | NCS, MSG, SNU |  | ??? | ??? | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
Sub Total 2.3 | [6 empty] | 34749.2633 | 0 | 10632.5588 | 0 | 10549.19 | 3180.5145 | 24362.2633 | 10387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10387 | 0 | 0 | 0 | 0 | 0 | 0 | 34749.2633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total 2 |  |  |  | Sub Total 2 |  |  | 1160115.1012 | 89924.9397 | 148652.2949 | 21446.8887 | 154260.0478 | 35143.4401 | 359502.6715 | 94754 | 60559 | 55831.43 | 92464 | 148295.43 | 4041 | 22226 | 990 | 27257 | 330865.43 | 41896 | 18310.27 | 21572.9208 | 81779.1908 | 29394.3321 | 415.573 | 891882.1371 | 268232.9641 | 319623 | 320918 | 320918 | 0 | 55925 | 87735 | 88349 | 23350 | 65559 | 320918
Objective 3:To support implementation of sustainable development and natural resource governance reforms through the successful execution of EITI.
3.1 | Technical and Reporting (IA main report, Forestry, BO, Mining Cadaster, SOE, Review of Artisenal Mining, Fasibility studies, Sub-national study, Implementation of recommendations, & other technical studies)
3.1.1 | Legislative institutionalization | Research to recommend legal options to EITI institunalization. Developing a draft EITI Law or amemdments to Sectoral Laws | NCS, Subcommittee, MSG | Consultancy | Research Report and Recommendations | Research Report and Recommendations accpeted by MSG | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.3 | EITI Reconciliation Report 2 &3 | [5 empty] | 270890 | 110740 | 83055 | 0 | 0 | 0 | 83055 | 77095 |  |  |  | 0 |  |  |  | 0 | 77095 | 0 | 0 |  | 0 |  |  | 270890 | 0 | [9 empty] | 0
3.1.3 | EITI Reconciliation Report 4 | [5 empty] | 248084 |  | 0 | 0 | 0 | 0 | 0 |  | 173898 | 74186 |  | 74186 |  |  |  | 0 | 248084 | 0 | 0 |  | 0 |  |  | 248084 | 0 | [9 empty] | 0
3.1.3 | EITI Reconciliation Report 5 | Independent Administrator and procure firm each year for the annual report (including scoping study) | MOBD, NCS, IA | Consulting | EITI Reconciliation Reports | Reports produced by deadline Reports approved by MSG Validation results on EITI Standard 2-6 | 370460 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 148184 |  | 148184 | 222276 | 370460 | 370460 | 370460 |  | 370460 |  |  |  |  | 370460
3.1.3 | EITI Reconciliation Report 5 | [5 empty] | 0 | [10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.3 | EITI Reconciliation Report 6 | [5 empty] | 0 | [10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.3 b | EITI Reconciliation Report Workshops | Report reconciliation and Reporting entities workshops-Main IA |  |  |  |  | 21543.4513 | 4439.4513 | 10484 | 0 | 0 | 0 | 10484 | 4744 | 1876 |  |  | 0 |  |  |  | 0 | 6620 | 0 | 0 |  | 0 |  |  | 21543.4513 | 0 | [9 empty] | 0
3.1.3 c | EITI Report Template Training | Template Training with IA and respective Agency |  |  |  |  | 7113 | [10 empty] | 0 |  |  | 140 | 140 | 140 | 3764 | 2165 |  | 5929 |  |  | 6069 | 1044 | 1044 | [8 empty] | 0
3.1.4 a | Forestry Reconciliation Report-1 | IA - First report |  | Consulting | Forestry Reconconciliation Report(s) | Report(s) approved by MSG | 160000 | 0 | 48000 | 80000 | 0 | 0 | 128000 |  |  | 32000 |  | 32000 |  |  |  | 0 | 32000 | 0 | 0 |  | 0 |  |  | 160000 | 0 | [9 empty] | 0
3.1.4 b | Forestry Reconciliation Report-2 | IA - First report |  |  |  |  | 0 | 0 |  |  | 0 | 0 | [5 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.4 c | Forestry Reconciliation Report Workshops | Reporting entities workshops-Forestry IA |  |  |  |  | 3952.4048 | 0 | 3952.4048 | 0 | 0 | 0 | 3952.4048 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 3952.4048 | 0 | [9 empty] | 0
3.1.4 d | Hydro Reconcillation Report | Independent Administrator and procure firm each year for the annual report (including scoping study) |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
| Hydro Reconcillation Report Meetings | [5 empty] | 223 |  | 0 | 0 | 0 | 0 | 0 | 223 |  |  |  | 0 |  |  |  | 0 | 223 | 0 | 0 |  | 0 |  |  | 223 | 0 | [9 empty] | 0
3.1.5 | Mineral and Gemstone Cadaster Phase 1 Consultant | Design Phase | MONREC, NCS, Subcommitte, MSG | Consulting | Preliminary, Intermediate and Final Report Mineral Cadastre Conceptual Design TOR for Phase 2 | Documents received and approved by MONREC and MSG | 119125.15 | 40017 | 40024 | 0 | 39084.15 | 0 | 79108.15 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 119125.15 | 0 | [9 empty] | 0
3.1.6 a | Mineral and Gemstone Pre-Cadastre Consultant | Pre-cadaster Working Group Consultant | MONREC, NCS, Subcommitte, MSG | Consulting | Training and on the job support Precadastre developed | No. of staff trained No. of Training Hours completed Completeness of Precadastre | 41390 | 0 | 0 | 0 | 12600 | 0 | 12600 | 15000 |  | 13790 |  | 13790 |  |  |  | 0 | 28790 | 0 | 0 |  | 0 |  |  | 41390 | 0 | [9 empty] | 0
3.1.6 b | Office Set Up Equipment for Pre Cadaster Working | [5 empty] | 21980.74 | 0 | 0 | 0 | 0 | 18168.74 | 18168.74 |  | 983 | 2771 | 58 | 2829 |  |  |  | 0 | 3812 | 0 | 0 |  | 0 |  |  | 21980.74 | 0 | [9 empty] | 0
3.1.6 c | Office Set up-Furniture for Pre-Cadastre working group | [5 empty] | 5632.769 | 0 | 0 | 0 | 0 | 3259.769 | 3259.769 |  | 2373 |  |  | 0 |  |  |  | 0 | 2373 | 0 | 0 |  | 0 |  |  | 5632.769 | 0 | [9 empty] | 0
3.1.6 d | ARC,GIS Software | [5 empty] | 40000 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 40000 | 0 |  | 40000 |  |  | 40000 | 0 | [9 empty] | 0
3.1.6 e | Maps, Stationery | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
| Gemstone Mapping Consultant | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.7 | Mineral and Gemstone Cadaster Phase 2 Consultant | Development and installation of cadaster. | MONREC, NCS, Subcommitte, MSG | Consulting | Deliverables outlined in TOR for Phase 2 | Indicators according to deliverables from TOR Phase 2 | 670000 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 670000 | 670000 | 670000 | 670000 |  | 134000 | 134000 | 134000 | 134000 | 134000 | 670000
3.1.8 | Mineral and Gemstone Cadaster Equipment | Purchase of IT equipment and furniture | MONREC, NCS, MOBD | Goods | Equipment and Furniture | Procurement report Purchase Receipt Inventory | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.11a. | Beneficial Ownership (ASI) | Development of Workplan, Communicaiton Plan, Capacity Building Plan and Pilot Project | NCS, Subcommittee, MSG | Consultancy | BO Work Plan, BO Communications Plan, BO Capacity Development Plan, BO Pilot Project | Deliverables approved by MSG | 120000 | 0 | 36000 | 0 | 0 | 84000 | 120000 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 120000 | 0 | [9 empty] | 0
3.1.11b. | Beneficial Ownership (Matheiu) | BO Template |  |  |  |  | 5685 | [9 empty] | 5685 | 5685 |  |  |  | 0 | 5685 | 0 | 0 |  | 0 |  |  | 5685 | 0
3.1.12 | Beneficial Ownership Meetings | BO workshops and Taskforce Meetings/ Template Training/ BO Press Condference | NCS, Task Force | Meeting and Workshop |  | No. of workshop/ meeting | 23824.3925 | 0 | 0 | 3657.1034 | 2001.05 | 6301.239 | 11959.3925 | 898 |  | 3260 | 2205 | 5465 |  |  |  | 0 | 6363 | 1002 | 0 | 1688.9575 | 2690.9575 |  |  | 21013.35 | 2811.0425 | 4500 | 4500 |  |  | 4500 |  |  |  |  | 4500
3.1.12 a | Beneficial Ownership | [5 empty] | 6525 | [9 empty] | 5998 | 5998 |  |  | 527 | 527 | 6525 | 0 | 0 |  | 0 |  |  | 6525 | 0 | [9 empty] | 0
3.1.12 c | Beneficial Ownership (Online Disclosure Form) | Development of Beneficial Ownership discloure Online system | DICA | Non Consulting Services |  |  | 8000 | [10 empty] | 0 |  |  | 7607 | 7607 | 7607 | 0 | 155 |  | 155 |  |  | 7762 | 238 | 238 |  |  |  | 393 |  |  |  |  | 393
3.1.14a. | Systematic Disclosure Feasibility Study | [5 empty] | 0 | [10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.4b | Systematic Disclosure Consultancy | [5 empty] | 0 | [10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
Sub Total 3.1 | [6 empty] | 2144428.9075 | 155196.4513 | 221515.4048 | 83657.1034 | 53685.2 | 111729.748 | 470587.4562 | 97960 | 179130 | 126007 | 13946 | 139953 | 0 | 0 | 8274 | 8274 | 425317 | 44766 | 2320 | 1688.9575 | 48774.9575 | 148184 | 0 | 1248059.865 | 896369.0425 | 1046242 | 1044960 | 1040460 | 0 | 509353 | 134000 | 134000 | 134000 | 134000 | 1045353
3.2 | Training and Capacity Development (Capacity Development for 3 MSG entities, MOBD, NCS & SNU capacity building)
3.2.1 a | Capacity Development | Implement Capacicty Development Plan (MSG, Private Sector, Governemnt, CSO, Media, EAOs, MOBD, NCS, Parliament and others) | NCS, MSG | Meeting and Workshop | Outputs defined in capacity development plan | Indicators defined in Capacity Development Plan Incld No. of participants, participant criteria (gender, stakeholder group, geographic location etc) Participant feedback | 33729.5837 | 8267.6968 | 4147.6666 | 720.018 | 11964.2991 | 8629.9032 | 25461.8869 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 33729.5837 | 0 | [9 empty] | 0
3.2.1 b | Capacity Development for Awareness | EITI Standard Awareness |  | Workshop and meeting/ Consultancy/ Goods |  |  | 0 | [10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.2.2 | Corrective Action Planning and Workshop | Corrective Actions and recommendation, SOE workshop, follow up action | NCS, Subcommittee, MSG | Workshop and meeting/ Consultancy/ Goods |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.2.3 | Capacity Development- Study Tour | MSG Study Tours | MSG | Non Consulting | Outputs defined in Study Tour Concept Note or Plan | Indicators from concpet note or plan Incld No. of participants, participant criteria (gender, stakeholder group, geographic location etc) Participant feedback and cascading activities | 24584.7365 | 0 | 0 | 0 | 12702.7365 | 0 | 12702.7365 |  | 567 |  | 11046 | 11046 |  |  |  | 0 | 11613 | 0 | 0 |  | 0 |  |  | 24315.7365 | 269 | 269 | 269 |  |  | 269 |  |  |  |  | 269
3.2.4 | Capacity Development- Int'l EITI events | EITI Global/ Regional Conferences and Board Meetings | MSG | Non Consulting | EITI Internnational Events attended | No. of events attended, No. of participants, cascade activities | 13380 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 12256 | 1124 | 13380 |  |  |  | 0 | 13380 | 0 | 0 |  | 0 |  |  | 13380 | 0 | [9 empty] | 0
3.2.5 | Financial Management Training (MOBD/NCS) | MOBD Financial management capacity development | NCS, Subcommittee, MSG | Consulting | Training and on the job support | No. of MOBD staff trained | 30520.8979 | 0 | 5969.7164 | 0 | 9261.1815 | 0 | 15230.8979 |  |  |  | 15290 | 15290 |  |  |  | 0 | 15290 | 0 | 0 |  | 0 |  |  | 30520.8979 | 0 | [9 empty] | 0
Sub Total 3.2 | [6 empty] | 102215.2181 | 8267.6968 | 10117.383 | 720.018 | 33928.2171 | 8629.9032 | 53395.5213 | 0 | 567 | 12256 | 27460 | 39716 | 0 | 0 | 0 | 0 | 40283 | 0 | 0 | 0 | 0 | 0 | 0 | 101946.2181 | 269 | 269 | 269 | 0 | 0 | 269 | 0 | 0 | 0 | 0 | 269
Sub Total 3 |  |  |  | Sub Total 3 |  |  | 2246644.1256 | 163464.1481 | 231632.7878 | 84377.1214 | 87613.4171 | 120359.6512 | 523982.9775 | 97960 | 179697 | 138263 | 41406 | 179669 | 0 | 0 | 8274 | 8274 | 465600 | 44766 | 2320 | 1688.9575 | 48774.9575 | 148184 | 0 | 1350006.0831 | 896638.0425 | 1046511 | 1045229 | 1040460 | 0 | 509622 | 134000 | 134000 | 134000 | 134000 | 1045622
GRAND TOTAL |  |  |  | Grand Total |  |  | 3500000.3962 | 253964.5421 | 384271.1398 | 108560.0785 | 258775.2552 | 160918.8905 | 912525.364 | 214854 | 247321 | 195724.43 | 141811 | 337535.43 | 4483 | 22226 | 9264 | 35973 | 835683.43 | 86662 | 20639.27 | 24800.7907 | 132102.0607 | 177578.3321 | 415.573 | 2312269.302 | 1187731.0941 | 1390533 | 1390397 | 1382628 | 0 | 587455 | 224235 | 222349 | 157350 | 199559 | 1390948
683604.3959
Note on B70: To be funded from the 500 K Cost Exptension