## 4th MSG
2017-2018 FY Workplan and Budget - 30th June 2017 (Yangon- Woodbased)
MSG Work Plan No. | Budget No. (WB-Format) | Objective | Activities | Implementing Agency | Outputs | Expense Category | Budget Detail | 3rd MSG Approved 8 Month Budget | Proposed Up to DEC, 2017 | Proposed Jan-Mar, 2018 | 64th MSG Approved Budget (2017-2018 FY) | Proposed Wrokplan | May 2017 | June 2017 | July 2017 | August 2017 | Sept 2017 | Oct 2017 | Nov 2017 | Dec 2017 | Jan 2018 | Feb 2018 | Mar 2018 | Remark
1.2.4 | 1.1.1 | Fully Functioning Secretariat | Coordination, Communications, Technical Support | NCS | Work Plan implementation, TOR, Implementation Manual, Job Descriptions | Consulting Services | 9 staff * 9 Months | 147500 | 81200 | 40600 | 121800
| 1.1.2 |  | Overhead Cost |  |  |  | operation costs |  | 27000 | 13500 | 40500
| 1.1.3 |  | Office Equipment & Funitures Purchase |  | Office Set up (Computers etc) |  | Equipment | 15000 | 15000 |  | 15000
| 1.1.4 |  | MOBD (office Cost & Travel) |  |  |  | MOBD (Office Costs and Travel) | 20000 | 20000 | 7500 | 27500
| 1.1.5 |  | MOBD Finanical Managerment Support |  |  |  | MOBD Financial Management Support | 30000 | 15000 |  | 15000
1.2.5, 1.2.10, 1.2.13, 2.1.14 | 2.4.1 | Develop plan to Implement Recommendations from 1st report | Meetings with Government Departments | Secretariat & T & R Subcommittee | Agreed actions, timetable & responsibilities | Meetings & Workshops | 6200 X 1 time | 6200 |  |  | 0
| 2.4.2 |  | Workshops and meetings on Implementing Recommendations of 1st Report |  |  |  | 5,000 X 3 times | 45000 |  |  | 0 | [12 empty] | To send official letter to each concerned department of Government for recommendation review workshop
1.2.6 |  | MSG Preparations for cadaster development | Form Cadaster Subcommittee & hold monthly meetings | Secretariat & W & G Subcommittee | Attendance record & mintues | Meetings & Workshops | covered under general subcommittee budget | 0 |  |  | 0
| 4.1.1 | Design of the cadaster | Procure a consultant | MONREC, & MSG Subcommittee | Design Documents | Consulting Services | 10% of the contract | 150000 | 75000 |  | 75000 | [12 empty] | According to Procurement Schedule
1.2.7 | 2.3.1 | Review of Artisanal and Small Scale Mining | Procure a consultant | Secretariat & T & R Subcommittee | Report | Consulting Services |  | 50000 |  |  | 0
1.2.12 | 2.2.1 | Develop Beneficial Ownership Definition and consultancy fee & Workshop | Benefical Ownership Consultancy | Secretariat & Subcommittee | Draft BO Roadmap and Pilot | Consulting Services | Consultancy Fees | 80000 | 80000 | 20000 | 100000 | [12 empty] | July 12th, deadline for EOI
| 2.2.2 |  | Beneficial Ownership Workshop |  | Agreed BO Roadmap | Meetings & Workshops | Workshop | 10000 | 10000 | 10000 | 20000
1.2.15 | 2.5.1, 2.5.2 | Determine the feasibility of including other sectors in MEITI | Feasibility Study 1 (hydro, forestry or fisheries) | Secretariat & T & R Subcommittee | Feasibility Study | Consulting Services |  | 50000 |  |  | 0
2.1.1 | 3.6.2 | Effective Training for MEITI Stakeholders | Training Plan Review Meeting | Secretariat & C & O Subcommittee | Updated Training Plan | Meetings & Workshops | covered under general subcommittee budget | 0 |  |  | 0
|  |  | Implement workshops under Training Plan |  | Workshops held | Meetings & Workshops | 5000 * 4 Times | 45000 | 20000 |  | 20000
2.2. | 3.6.3 | Study tour |  | MSG |  |  |  | 30000 |  |  | 0
3.2.1 | 1.2.1 | Effective Operation of MSG | MSG Meetings | Secretariat | Attendance record & mintues | Meetings & Workshops | 3,800 x 6 | 19000 | 19000 | 11400 | 30400
3.2.2 | 1.2.2 | Effective operation of Subcommittees | Subcommittee Meetings | Secretariat | Attendance record & mintues | Meetings & Workshops | 600 x 15 | 15000 | 9000 | 3600 | 12600
3.2.7 | 2.1.1 | Production of 2 and 3rd MEITI Report | Procure and support consulting firm to prepare report | Secretariat & T& R Subcommittee | Report | Consulting Services | 260,000 X 50% 280000 * 50% | 130000 | 140000 | 140000 | 280000
| 2.1.2 |  | Procure and support consulting firm for Forestry |  |  |  | 160,000 X 50% | 80000 | 80000 | 80000 | 160000
| 2.1.3 |  | Reporting Entities Workshop (Oil, Gas, Mining, Gemstones) |  |  |  | 7500 * 2 Times |  | 15000 |  | 15000
| 2.1.4 |  | Reporting Entities Workshop (Forestry) |  |  |  | 7000 * 1 Time |  | 7000 |  | 7000
4.1 | 3.2.1 | Communications | MEITI Website Redesign | Communications staff, C & O Subcommittee | Updated MEITI Website Redesign | Consulting Services | 15000 | 15000 | 5000 |  | 5000
| 3.1.1 |  | Communications Workshop | Communications staff, C & O Subcommittee | Updated Communications Strategy & Plan | Meetings & Workshops | 5,300 X 2 days | 10600 | 8178 |  | 8178
| 3.2.4 |  | EITI Public Forum | Communications staff, C & O Subcommittee | Forum | Meetings & Workshops | 6,000 X 1 day | 6000 |  |  | 0
|  |  | MEITI 2nd and 3rd Report and IEC, Annual Progress Report Publication Dissemination Activities ( MEITI Flyer, 2016 EITI Standard, Implementation Manual) Translation | Communications staff, C & O Subcommittee | MEITI Flyer - 10,000 * .3 = $ 3000 T-Shirt/Sport Shirt - 100 * 50 = $ 5000 2016 EITI Standard - 2000 * 2 = $ 4000 APR - 1000 * 3 = $ 3000 Implementation Manual - 100 * 5 = $ 500 Translation - $1500 | Meetings & Workshops | 1,800 X 6 times | 10800 |  | 17000 | 17000 | [12 empty] | MEITI Flyer - 10,000 * .3 = $ 3000 T-Shirt/Sport Shirt - 1000 * 5 = $ 5000 2016 EITI Standard - 2000 * 2 = $ 4000 APR - 1000 * 3 = $ 3000 Implementation Manual - 100 * 5 = $ 500 Translation - 1500
4.2.7 | 3.7.1 | Subnational Committee Formation & Operation | Subnational Meetings, Workshops | C & O Subcommittee | Minutes and TORS | Meetings & Workshops | 25000 X 4 times 25000 * 6 Times | 100000 | 100000 | 50000 | 150000
4.3.5 | 1.3.1 | Review of Workplan and Preparation Progress Activity Report | Annual Workplan Review Workshop | W & G Subcommittee | Attendance record, minutes & Updated Workplan | Meetings & Workshops | 6,000 X 2 days | 12000 |  |  | 0
|  | TOTAL BUDGET (2017-2018 FY) | [5 empty] | 1077100 | 726378 | 393600 | 1119978
[5 empty] | 1650 | 20 | 11 | 94
[5 empty] | 750 | 20 | 5 | 100
14100
|  |  |  | 27800 |  |  |  | 15000
29100
10700
Note on H22: mineral cadastre 2; workplan and gov 4; comms 4; technical 5.

## Update-2Yrs
Myanmar EITI MSG Work Plan ( April 2017-Dec 2019 )
Comparison Table for Discussion Purpose for MSG members
Activity No | Update New Version | 2016 (Jan-March) | 2016-17 | 2017-18 | April,2018 - March-2019 | April, 2019 - December,2019 | Remarks
Objective 1 : Contribute to broader reform for resource governance
1.2.1 | Implement agreed plan regarding legislative institutionalisation of EITI in Myanmar, including holding workshops and meetings |  | 31000 | 21000 | 15000 | 0 | Reduce budget bez one year is enough for legal review but we put 10000 extra for 2017
1.2.2 | Carryout legal study on existing bill and laws for decision making of preparing new EITI bill or not. (Comparative study on both national and international) Implement the MSG decision(s) in regard to EITI Related Legislation Workshops and Meetings to develop legislation if needed |  | 20000 |  | 100000 |  | Procurement for consultant (local / International) to do legal review and conduct for 4 workshops with each constituency & MSG (can combine with MSG meeting or workshop)
1.2.3 | Government EITI Coordination 1. Establish inter-departmental EITI working group under each key EITI-related ministry (EITI Special Units) 2. Review and strengthen existing government EITI coordination mechanism | [5 empty] | To review international experiences and share to MSG
1.2.4 | Ministry of Planning and Finance is taking responsibility of Financial Management and National Coordination Secretariat Office is taking care of Coordination, Technical and Communication. | 8540 | 64600 | 44600 |  |  | NCS Office
| MEITI-NCS office for secretariat function with MOU between MOPF and RI | 11240 | 134880 | 97080 | 230000 | 30000
1.2.5 | Awareness Raising for Identifying and planing the support required to the government (central and regional offices) to understand and calculate: (Workshops, Trainings, Meetings, Events, etc..) 1. regional/ local extractive industries contribution to national economy and 2. production and export volumes and pricing | 0 | 6000 | 6000 | 10000 | 10000 | Yearly meeting for 4 years
1.2.6 | 1. Ministry of Natural Recources and Environemntal Conservation -MONREC to establish a comprehensive cadastre/ registry of licenses in line with EITI requirement 2. EITI related ministries |  | 0 |  | 425000 | 500000
1.2.7 | Carry out review of the illegal and artisanal and small scale mining (ASM) sector to understand potential contribution to national economy and estimation of production data also refer to recommendations of the scoping study. |  | 50000 |  | 100000 | 50000 | to do at 4 areas-Kayin, Tanintharyee, Mdy,Shan
| EITI related research according to MSG |  |  | 25000 | 30000 | 10000 | New Activities-follow MSG decision
1.2.8 |  | 0 | 0 | 0 | 0 | 0 | To be finished by 2015.
1.2.9 | Government (including SOE) needs to identify its level of ownership in the sector to be also refer to, and build on IA recommendations. | 0 | 0 | 0 | 30000 | 20000 | In lin ewith IA recommendation combine 1.2.10
1.2.10 | Government to review and strengthen availability of EITI related data among SOEs for disclosure in EITI report |  | 2000 | 2000
1.2.11 |  |  | 10000 | 10000
1.2.12 | Carry out a study to map and identify levels of beneficial ownership in the extractive sectors in Myanmar also refer to IA's recommendations on beneficial ownership. |  | 45000 | 0
1.2.13 | 1. Government to agree procedure for disclosure of information related to the allocation of licenses. 2. Disclose information about bidding process including list of applicants and the yearly bid criteria also refer to EITI 2016 Standard Requirement |  | 1000 |  | 5000 | 2000
1.2.14 | Workshop to explore best practice on contract disclosure and social expenditure, based on this workshop MSG to make recommendations on contract disclosure and social expenditures |  | 8000 | 0 | 15000 | 5000 | Both for Government and Private Sectors in all Oil, Gas, Mining, Forest, Hydro, Pearl
1.2.15 | Carry out a feasibility study on the potential inclusion of the hydropower sector in the EITI Reoprting Process. | 0 | 25000 |  | 50000 |  | It not wider scope and base on previous study, reduced budget
Budget Sub Total For Objective-1 |  | 19780 | 397480 | 205680 | 1010000 | 627000
Objective 2 : Create enabling environment for EITI
2.1.1 | MSG Communications and Outreach Sub-Committee to review and amend the training plan every quarter and ensure that training activities are carried out accordingly. |  | 70000 | 70000
2.2.1 | Training, Workshop, Events plan and implement for MSG members and each stakeholders based on need and requirement | 0 | 0 | 0 | 45000 | 15000
2.2.2 | MSG study tours and MEITI delegation/ representatives to attend EITI Board meeting as appropriate |  | 42000 | 30000 | 42000 | 30000 | once in Yearly MSG study tour and International BOD meeting bi annual
2.2.3 | MEITI MSG delegation to attend EITI Global Conference – held every 2 or 3 years | 25000 | 0 |  | 30000 | 30000 | According to this year invitation, 4 PPL only invited. Therefore reduce budget.
2.2.4 | Government training and capacity development (as requested by government) 1. Basic natural resource governance training to EITI related (Union) ministries 2. Basic natural resource governance and EITI training to regional governments (especially from resource rich states and regions) 3. Advance Natural Resource Governance and Reporting Practice Training to MEITI Government, Working Group and Working Group/Focal Group from Each EITI Related Government Agencies 4. Fiscal regime in EI related training 5. International accounting standard and project financing and evaluation training | 7000 |  |  | 5000 | 5000 | For resource person fees
2.2.5 | Civil Society Organisation (CSOs) training and capacity development Training activities to be developed as per Training Needs Assessment | 7000 |  |  | 5000 | 5000
2.2.6 | Private Sector training and capacity development Training activities to be developed as per Training Needs Assessment | 7000 |  |  | 5000 | 5000
| Financial Consultant- to build up MOF secretariat team' financial management | 15000 | 15000 |  | 15000 | 15000 | To support MEITI office (for full function)
| Organize a minining governance and an oil and gas governance and forestry sector, Hydro-power, Pearl Sector workshop every year. |  | 0 | 0
2.3.1
2.3.2 | Political Economy Study (Pre-Scoping Study) |  |  |  | 50000
Budget Sub Total For Objective-2 |  | 61000 | 127000 | 100000 | 197000 | 105000
Objective 3 : Prepare and facilitate the process for implementing
3.1.1
3.1.2 | Prepare and Secure for development partners for upcoming activities and insecure by MDTF
3.1.3 | Secure increased government contribution to EITI (Advocacy to Ministry) |  | 10000
3.1.4 | Prepare and secure core funding for MEITI Coordination Office
3.2.1 | Hold MSG meeting every two months and ad-hoc meeting | 5300 | 42000 | 42000 | 26600 | 19000 | MSG meeting was held one time in every two months and it will be held urgently if it is need upon the request
3.2.2 | Review operation of MSG subcommittees, develop guideline and implement recommendations and hold subcommittee meetings | 0 | 15000 | 15000 | 18000 | 15000 | Currently, there are 4 to 5 Sub-committees and held before the MSG meeting. The ad-hoc meeting will also be held depend on the request and emergency committee will also set up.
3.2.3 | Implemented Already |  | 130000 | 130000 |  |  | for 3 reports only
3.2.4 | Conduct one scoping study | [5 empty] | Cover under 3.2.3
3.2.5 | 1. MSG to agree scope and definition of materiality threshold for the first report based on the results of the scoping study 2. Reconciler to develop reporting templates with MSG in line with agreed scope 3. MSG to approve the reporting templates | [5 empty] | Cover under 3.2.3
3.2.6 | Training on EITI reporting and templates for all Reporting Entities |  |  |  | 37500 | 37500 | Cover under 3.2.3
3.2.7 | Preparation and production of annual MEITI report – 2017, 2018 and 2019 (3 years) |  |  |  | 360000 |  | Cover under 3.2.3
3.2.8 | Approve and Launch Of MEITI Report by MSG |  |  |  | 20000 |  | Cover under 3.2.3
3.3.1 | Prepare for the 3rd Report including procurement of Reconciler | [5 empty] | Cover under 3.2.3
3.3.2 | Production of 2nd, 3rd, 4th MEITI Report |  |  |  | 30000 |  | Cover under 3.2.3
3.4.1 | Engage in validation, review and approval of validation report (2017, 2019) | [5 empty] | Cover under 3.2.3
Budget Sub Total For Objective-3 |  | 5300 | 197000 | 187000 | 492100 | 71500
Objective 4: Increase the accessibility of data (Communication and Information Sharing)
4.1 | Widespread communication and dissemination of MEITI report, ensuring contribution to public debate including e.g.: - Press Release - (Media) Including TV, Radio, Print, events and activities | 3500 | 70000 | 60000 | 35000 | 15000
4.2.1 | MEITI Website (regular updating and maintenance) |  | 1000 | 1000 | 1000 | 1000 | For 3 Years
4.2.2 | MEITI Secretariat to establish online and physical 'library' of EITI related information for EITI stakeholders (where the information is not publicly available, it should be approved by MSG) |  | 2500 | 2500 | 2500 | 500 | Buy Book for Physical Library at Secretariat Office
4.2.3 | Review and Update MEITI communications plan/strategy
4.2.4 | Implement communications plan/strategy including e.g. information, education and communication materials, outreach events, workshops, seminars etc. |  | 31000 | 31000 | 10000 | 5000
4.2.5 | Possible Outreach Events to include: 1. Seminars and workshops (approx. 15) 2. National EITI Conference | [5 empty] | Cover under 4.2.4
4.2.6 | Outreach events for each constituency group | [5 empty] | Cover under 4.2.4
4.2.7 | To conduct outreach events to establish 14 subnational coordination units, and to support the effective functioning of subnational coordination units, including the organization of events and activities outlines in subnational coordination unit strategies | 1100 | 150000 | 150000 | 30000 | 30000 | plan to form all SNCU in 2017 and 2019 and 2018-19 for follow up
4.3.1 | MSG to review and evaluate reports from subnational coordination units and determine coordinate consistent response to issues raised. (PAR research etc) |  | 20000 |  | 5000 | 5000 | For 2017 and 2018
4.3.2 | MSG to review IA’s recommendations in every annual report and agree an action plan to implement them accordingly. |  |  |  | 10000 | 10000
4.3.3 | Also refer to IAs recommendations in the EITI Report, procure a consultant to carry out an EITI data needs assessment and then work with government and relevant stakeholders to put in place an effective EITI electronic/online, integrated data management system accordingly. |  | 10000 |  | 20000 | 10000
4.3.4 | MSG Workplan and Governance Sub-Committee to regularly review the WP and monitor progress against activities, and to discuss WP progress and priorities at every MSG meeting as appropriate |  | 0 | 0 | 0 | 0 | we can do other MSG meeting and sub committee meeting. Therefore reduced budget.
4.3.5 | MSG to review annual progress (workplan), produce annual activity/progress report and send to International Secretariat and organize an annual focused workshop to review and update the MEITI Workplan |  | 5000 | 5000 |  |  | according to 2015, there is no cost for annual progress report and work plan review. This cost for printing and translaion for report.
Budget Sub Total For Objective-4 |  | 4600 | 289500 | 249500 | 113500 | 76500
Total Budget |  | 90680 | 1010980 | 742180 | 1812600 | 880000
Actual Budget |  |  |  | 1119978
|  |  |  | 3500000 | 1119978 | 1812600
|  |  |  | 2380022 | 3500000 | 880000
[5 empty] | 2380022 | 2692600 | -312578
Note on C9: Author: Jan, Feb and March 2016
Note on C10: Author: for March 2016
Note on D19: Author: 2 dissemination work shop for each groups
Note on D27: Author: Board Meeting & Study Trip
Note on E27: Author: one Stuy Trip only