## WP_to_Sep_21_Combine_All_Budget
2020 EITI WORK PLAN OF MYANMAR
No. | EITI standard/ requirement | Categories of activities | Activities | Main Objective | Objective per activity | Outputs | Outcomes | Responsible Department | Timeline | [20 empty] | No.of Unit | Unit type | Amount (per each) | Total | Current Budget and Funding Soruce |  |  |  |  | Amount need to receive | Potential funding source | Deadline | Indicators | Source and means of verification | Risk/Assumption
[9 empty] | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-20 | 2020-05-20 | 2020-06-20 | 2020-07-20 | 2020-08-20 | 2020-09-20 | 2020-10-20 | 2020-11-20 | 2020-12-20 | 2021-01-21 | 2021-02-21 | 2021-03-21 | 2021-04-21 | 2021-05-21 | 2021-06-21 | 2021-07-21 | 2021-08-21 | 2021-09-21 |  |  |  |  | WB(MDTF) | Nathan Associate | NRGI | Forest Trend | Others
1 | Implementation structure
|  | 1.1 Donor Consultation Group meeting | Meeting, workshop | Objective 2 : To create an enabling environment for the effective implementation of the EITI standard. | To discourse about the implementation structure of MEITI according to the notification forming the donor consultation group dated 5th November, 2019 | Keep to disucss the sustainablity of EITI process not to effect shortage | Assured financial sources for the sustainability of EITI implementation in Myanmar | MOBD, Donor Consultation Group | [21 empty] | 7 | Times | 350 | 2450 | [5 empty] | 2450 |  |  | Meeting minutes, Proposal | Development partners, Implementation structure | It was not discussed in MSG meeting before the group was formed. | bar: 2020-02-01 to 2020-04-20; 2020-06-20; 2020-08-20; 2020-10-20; 2020-12-20
|  | 1.2 Organizational Development Consultant | Consultant | [26 empty] | 1 | Times | 31500 | 31500 |  | 31500 |  |  |  | 0 | bar: 2020-05-20
2 | Corrective Actions and recommendations, SOE workshop , Follow up actions | [37 empty] | 0
|  | 2.1 SOE workshop (Workshop and Pre Meeting) | Meeting, workshop | Objective 2 : To create an enabling environment for the effective implementation of the EITI standard. | To follow the EITI standard and Myanmar Sustainable Development Plan | Conprehend the current practice of SOE | Achievement of satisfactory implementation of EITI activities and undertaking corrective actions as reommended by International Board from first validation 2018 | Leading Committee, Working CommitteeMSG, NCS, Governments Departments, MOBD | [21 empty] | 3 | Times | 8700 | 26100 | 3883 |  |  | 5000 |  | 22217 | Forest Trend (5000) | 16th April - 2021 | Workshop report, Pre-meeting minutes, Number of participants, Action plan | Progress of SOE reform in relevant government departments | bar: 2020-06-20; 2020-09-20; 2020-12-20
|  | 2.2 Second validation workshop /validation group meeting | Meeting, workshop | Objective 2 : To create an enabling environment for the effective implementation of the EITI standard. | To recover the first validation recommendation | Follow-up actions could be discussed for 12 corrective actions | Achievement of satisfactory implementation of EITI activities and undertaking corrective actions as reommended by International Board from first validation 2019 | Leading Committee, Working CommitteeMSG, NCS, Governments Departments, MOBD | 2020-04-20: 1; 2020-05-20: 1; 2020-06-20: 2; 2020-07-20: 2; 2020-08-20: 2; 2020-09-20: 2; 2020-10-20: 3; 2020-11-20: 2; 2020-12-20: 3; 2021-01-21: 2; 2021-02-21: 3; 2021-03-21: 2 | 25 | Times | 350 | 8750 | 4200 |  |  |  |  | 4550 |  | 16th April - 2021 | Consultation, Meeting, Workshop, Action plan | Progress of corrective actions and EITI requirements, 2nd validation result
|  | 2.3 Contract transparency workshop | Meeting, workshop | Objective 3 : To support implementation of sustainable development and natural resource governance reforms through the successful execution of EITI. | To plan for disclosing contracts with a clear timeframe and to address the barriers to comprehensive disclosure. | Gain the information about requirements and barriers to disclose the contracts | Pave the way to government, CSO and companies to make easy to disclose the contract | Leading Committee, Working CommitteeMSG, NCS, Governments Departments, MOBD | [21 empty] | 3 | Times | 3500 | 10500 |  |  | 10000 |  |  | 500 | NRGI | 1st January - 2021 | Workshop report, Pre-meeting minutes, Number of participants, Action plan | Rate of contarct disclosure in extractive industry | MATA will provide ( TBC) | bar: 2020-05-20; 2020-07-20; 2020-09-20
|  | 2.4 Systematic disclosure and mainstreaming (Consultant) | Feasibility Study |  | To encourage the integral part of government management for extractive sector beyond the EITI report | Implement the open data system integrating with national portal | Gain the improvement of government syestem to open data by default | Leading Committee, Working CommitteeMSG, NCS, Governments Departments, MOBD | [21 empty] | 1 | Times | 40000 | 40000 |  | 40000 |  |  |  | 0 |  | 2019 - 2021 | Workshop report, Pre-meeting minutes, Number of participants, Action plan | National web portal, Ministry website and Government report | bar: 2020-07-20
|  | 2.5 Systematic disclosure and mainstreaming | Meeting, workshop | [26 empty] | 2 | Times | 500 | 1000 |  | 1000 |  |  |  | 0 |  | 2019 - 2021 | bar: 2020-08-20; 2020-10-20
|  | 2.6 Project level reporting workshop | Meeting, workshop |  | To help strengthen government's position to negiotiate contracts with companies. To encourage the MSGS to identify legal instruments: contracts, concessions, production-sharing agreements, licenses, leases, titles, permits, and other agreemetns. | Can be seen the payments of each projects in EITI report | Government can address tax evasions, civil society can compare payments to governments with actual activities and production with specific sites and companies can benefit through managing communities' expectation by better udnerstanding how extractive companies operate | Leading Committee, Working CommitteeMSG, NCS, Governments Departments, MOBD | [21 empty] | 3 | Times | 1000 | 3000 |  | 1000 |  |  |  | 2000 |  | 31st Dec - 2020 | Workshop report, Pre-meeting minutes, Number of participants, Action plan | EITI reports | bar: 2020-06-20 to 2020-07-20; 2020-09-20
3 | 2019 EITI standard awareness | [37 empty] | 0
|  | 3.1 Translation | Corrective actions and other related document | Objective 1 : To acquire & disseminate accurate, correct and up-to-date information regarding the management of natural resources and associated material revenues in a timely manner and to make the information publicly available. | To exchange the EITI information from local to international | Local people are able to access the EITI information in burmese. On the otherhand, the activities and inforamtion of MEITI will go to Internationl enviroment including EITI secretariat | Translation could make EITI knowledge exchange between local and international | Service Provider, NCS , MOBD | [21 empty] | 1 |  | 12000 | 12000 | [5 empty] | 12000 |  |  | EITI standard document | Percentage of awareness on EITI standard by public and policy makers | bar: 2020-05-20
|  | 3.2 Printing and Publication | EITI standard related document |  | To share report and IEC materials with public to make easy to understand the EITI related information | EITI information is accessible to public | Ensure the EITI information including definitions are accessible to public | Service Provider, NCS , MOBD | [21 empty] | 1 | Times | 4061 | 4061 | 3660 |  |  |  |  | 401 |  |  | Number of documents | Percentage of awareness on EITI standard by public and policy makers | bar: 2020-05-20
|  | Other IEC Materials Printing | [27 empty] | 1 | Times | 4000 | 4000 | [5 empty] | 4000 | bar: 2020-08-20
4 | Beneficial ownership
|  | 4.1 BO taskforce meeting | Meeting | Objective 3 : To support implementation of sustainable development and natural resource governance reforms through the successful execution of EITI. | To continue implementing the remaining activities and to ensure BO reporting in the year 2020 | BO task force meeting is one of the supporters to review the national laws and regluations to assess whether the BO and Political Expeosed Person (PEP) definations developed by the MEITI align fully with the existing national legislation and developing amendments as necessary.Advices for BO activities to MEITI working committee meeting to have approval was came out | Implementation of the BO workplan, initiation with the sector sepcific approach to BO disclosure and discussion to tackle the BO activities. Presidential notification was out due to the effort of BO task force in order to push the companies to discloe their BO related data. There was a chance to recieve relevant international training related with BO. | NCS / DICA/ BO task force/ Working committtee | [21 empty] | 8 | Times | 3500 | 28000 | 3500 |  |  |  |  | 24500 |  |  | Meeting minutes, Work plan, Action plan | Implemenation of BO process under EITI standard timely | bar: 2020-06-20; 2020-08-20; 2020-10-20; 2020-12-20; 2021-02-21; 2021-04-21; 2021-06-21; 2021-08-21
|  | 4.2 BO online form training for additional companies | Training / workshop |  | To make understand the BO template to fill out BO data | Companies came to understand to fill out their BO related data in template which will be disclosed in DICA website for public | Public can access these BO data in order to varify | NCS/ DICA/ BO task force | [21 empty] | 3 | Times | 1000 | 3000 | [5 empty] | 3000 |  |  | Number of trainings, Number of participants | Implemenation of BO process under EITI standard timely | bar: 2020-07-20 to 2020-09-20
|  | 4.3 BO Press conference | Press conference | Objective 1 : To acquire & disseminate accurate, correct and up-to-date information regarding the management of natural resources and associated material revenues in a timely manner and to make the information publicly available. | To accept the questions and suggestions from organizations and public | Receive the feedback from public those who interested in and point out the strength and weakness of BO data disclosure | Increased awareness and improved publiic debate on Extractive Industry issues support to Extractive sector reform | NCS/ DICA/ BO task force | 2020-09-20: 2 | 2 | Times | 3000 | 6000 | [5 empty] | 6000 |  |  | Number of media coverage, Number of articles | Implemenation of BO process under EITI standard timely
|  | 4.4 BO consultant support service | Consultant | Objective 3 : To support implementation of sustainable development and natural resource governance reforms through the successful execution of EITI. | To contribute the expense of focal agency when they coordinate with NCS travelling to Naypyitaw and Mandalay to give the training for companies and to meeting with government agencies | Opportunity comes to focal agency to learn about ongoing BO process | Readiness for government when they came to position to host the BO data diclosure process | Consultant, NCS, DICA | [21 empty] | 3 | Times | 500 | 1500 | [5 empty] | 1500 |  |  | Number of field visit | Implemenation of BO process under EITI standard timely | bar: 2020-07-20 to 2020-09-20
|  | 4.5 BO website development for BO data | Web developer |  | To modify the website features including the additional information regarding the BO data | Latest BO information are updatable | BO data disclosure is accessible for public | Web Developer, NCS, DICA | [21 empty] | 1 | Times | 50000 | 50000 |  | 50000 |  |  |  | 0 |  | ASAP | BO template form in DICA Website | Implemenation of BO process under EITI standard timely | bar: 2020-06-20
|  | 4.6 BO verification | Consultant |  | To ensure the accuracy of ownership information | Ensure the truthness of BO data | BO data disclosure is accessible for public | Consultant, NCS, DICA | [21 empty] | 1 | Times | 30000 | 30000 | [5 empty] | 30000 | NRGI | 17th January -2020 | Consultant's Report, Completion of assigment | Implemenation of BO process under EITI standard timely | bar: 2020-08-20
|  | 4.7 BO awareness raising | Workshop |  | To explain about beneficial ownership | Provide BO awareness rasing to additional companies in 2020, public and SNU trip | Publice acquire the knowledge the definition of BO and PEP in order to analyze the issue of corruption | NCS/ DICA/ BO task force | [21 empty] | 1 | Times | 1000 | 1000 | [5 empty] | 1000 |  |  | Number of trainings, Number of participants | Implemenation of BO process under EITI standard timely | bar: 2020-07-20
|  | 4.8 BO legal review ( Consultant) | Consultant |  | To make certain how legistation requires ownership disclosure | Knowing the requirement of amendments and a timeframe for working on BO related laws | Introduction of beneficial ownership transparency through amendments to company laws or other dedicated legal instruments. | Consultant | [21 empty] | 1 | Times | 20000 | 20000 |  | 20000 |  |  |  | 0 |  |  | Consultant Report, Recommendation , Action Plan | Implemenation of BO process under EITI standard timely | bar: 2020-05-20
|  | 4.9 BO report | Printing | [26 empty] | 1 | Times | 3000 | 3000 | [5 empty] | 3000 | bar: 2020-09-20
|  | 4.10 BO priniting | IEC materials | Objective 1 : To acquire & disseminate accurate, correct and up-to-date information regarding the management of natural resources and associated material revenues in a timely manner and to make the information publicly available. | To share report and IEC materials with public to make easy to understand the definition of BO and why it need to be disclosed | BO information is accessible to public | Ensure the BO information including definitions are accessible to public | BO Task Force, NCS, DICA, MOBD | [21 empty] | 1 | Times | 1000 | 1000 | [5 empty] | 1000 |  |  | Number of IEC, Coverage BO information to public | Implemenation of BO process under EITI standard timely | bar: 2020-09-20
|  | 4.11 BO ( Online disclosure form) | Development of beneficial ownershiop disclosure online system | [26 empty] | 1 | Times | 238 | 238 | [5 empty] | 238 | bar: 2021-03-21
5 | Website Maintainance | [37 empty] | 0
|  | 5.1 MEITI website maintainance | Web developer | Objective 1 : To acquire & disseminate accurate, correct and up-to-date information regarding the management of natural resources and associated material revenues in a timely manner and to make the information publicly available. | To set up open data format for MEITI reports data | Increasing awareness on the need for transparency and improve pubic debate on Extractive issues support to the Extractive sector reform | Increased awareness and improved public debate on Extractive Industry issues support to Extractive sector reform | Service Provider, NCS , MOBD | [21 empty] | 2 | Times | 1000 | 2000 | 1500 |  |  |  |  | 500 |  |  | EITI informamtion, Report, News, open data..etc | Updatable | bar: 2020-08-20; 2021-08-21
|  | 5.2 Web-portal and infographic | Web developer | [5 empty] | 2020-04-20: 2 | 2 | Times | 3000 | 6000 | 3000 |  |  |  |  | 3000
6 | Report launch, Public debate and Printing | [37 empty] | 0
|  | 6.1 4th report launch and public debate | Public Debate Workshop | Objective 1 : To acquire & disseminate accurate, correct and up-to-date information regarding the management of natural resources and associated material revenues in a timely manner and to make the information publicly available. | To make sure the information is widely accessible and distributed | Accepting the recommendations from public directly and repliying the public concern | Increased awareness and improved public debate on Extractive Industry issues support to Extractive sector reform | MSG, NCS, MOBD, SNU | [21 empty] | 2 | Times | 2500 | 5000 | 5000 |  |  |  |  | 0 |  |  | Number of report launch and public debate,Nuber of participants, Public Debate report | Follow up actions on the discussion points in public debate | bar: 2020-07-20 to 2020-08-20
|  | 6.2 5th report launch and public debate | Public Debate Workshop |  | To make sure the information is widely accessible and distributed | Accepting the recommendations from public directly and repliying the public concern | Increased awareness and improved public debate on Extractive Industry issues support to Extractive sector reform | MSG, NCS, MOBD, SNU | [21 empty] | 2 | Times | 2500 | 5000 |  | 5000 |  |  |  | 0 |  |  | Number of report launch and public debate,Nuber of participants, Public Debate report | Follow up actions on the discussion points in public debate | bar: 2020-08-20 to 2020-09-20
|  | 6.3 4th MEITI Report Print | 4th report translation and printing | [26 empty] | 1 | Times | 10650 | 10650 | 7500 |  |  |  |  | 3150 | bar: 2020-05-20
|  | 6.4 5th EITI Reconciliation report and 3rd,4th Forestry Report | Independent Administrator and procure firm each year for the annual report ( including scoping study) | [26 empty] | 1 | Times | 222276 | 222276 | 222276 |  |  |  |  | 0 | bar: 2020-05-20
|  | 6.5 5th Report Print and Translation | 5th report translation and printing |  | To make sure the information is widely accessible and distributed | Accepting the recommendations from public directly and repliying the public concern | Increased awareness and improved public debate on Extractive Industry issues support to Extractive sector reform | MSG, NCS, MOBD, SNU | [21 empty] | 1 | Times | 12000 | 12000 |  | 12000 |  |  |  | 0 |  |  | Translated Report | bar: 2020-05-20
|  | 6.6 3rd and 4th Forestry Report Print and Translation | Foresrty Report translation and printing |  | To make sure the information is widely accessible and distributed | Accepting the recommendations from public directly and repliying the public concern | Increased awareness and improved public debate on Extractive Industry issues support to Extractive sector reform | MSG, NCS, MOBD, SNU | [21 empty] | 1 | Times | 12000 | 12000 | [5 empty] | 12000 |  |  | Translated Report | bar: 2020-05-20
|  | 6.7 Forestry Reort Launch | Report Launch |  | To make sure the information is widely accessible and distributed | Accepting the recommendations from public directly and repliying the public concern | Increased awareness and improved public debate on Extractive Industry issues support to Extractive sector reform | MSG, NCS, MOBD, SNU | [21 empty] | 1 | Times | 5000 | 5000 | [5 empty] | 5000 |  |  | Number of report launch and public debate,Nuber of participants, Public Debate report | bar: 2020-05-20
|  | 6.8 5th MEITI Report Analysis Workshop | [27 empty] | 1 | Times | 4000 | 4000 | [5 empty] | 4000 | bar: 2020-12-20
|  | 6.9 3rd , 4th Forestry Analysis Workshop | [27 empty] | 1 | Times | 4000 | 4000 | [5 empty] | 4000 | bar: 2020-12-20
|  | 6.10 6th and 7th MEITI Reconcillation Report | [27 empty] | 1 | Times | 300000 | 300000 | [5 empty] | 300000 | bar: 2020-10-20
|  | 6.11 Template Training and Reconcillation Meeting for 6 Report, 6 and 7 Report | [27 empty] | 4 | Times | 3000 | 12000 | 1044 |  |  |  |  | 10956 | bar: 2020-08-20; 2020-11-20 to 2021-01-21
7 | Press Conference for report | [37 empty] | 0
|  | 7.1 Press conference for 4th report | Press release, articles, report | Objective 1 : To acquire & disseminate accurate, correct and up-to-date information regarding the management of natural resources and associated material revenues in a timely manner and to make the information publicly available. | To accept the questions and suggestions from organizations and public | Receive the feedback from public those who interested in and point out the strength and weakness of report and information gap | Increased awareness and improved publiic debate on Extractive Industry issues support to Extractive sector reform | MSG, NCS, MOBD | [21 empty] | 0 |  |  | 0 | [5 empty] | 0 |  |  | Media Coverage (Number of media participant), Media briefing notes | Acknowledging about how media understand EITI matters and bring these matter to public , the response of public on the presentation of media
|  | 7.2 Press conference for 5th report | Press release, articles, report |  | To accept the questions and suggestions from organizations and public | Receive the feedback from public those who interested in and point out the strength and weakness of report and information gap | Increased awareness and improved publiic debate on Extractive Industry issues support to Extractive sector reform | MSG, NCS, MOBD | [21 empty] | 1 | Times | 3000 | 3000 |  | 3000 |  |  |  | 0 |  |  | Media Coverage (Number of media participant), Media briefing notes | Acknowledging about how media understand EITI matters and bring these matter to public , the response of public on the presentation of media | bar: 2020-04-20
8 | SNU trip | [28 empty] | 0 | [8 empty] | 0
|  | 8.1 Kayah | Meeting, workshop |  | To make a bridge between the coordination of national and subnational units in Extractive Industry | Create the space to work out a deal on EITI related challengaes , advantages and conflicts in order to make improve | Improvement of EITI awareness and effective implementation of EITI in the sub-national level | MSG, NCS, MOBD, Sub-Region Government | [21 empty] | 1 | Times | 3000 | 3000 |  |  |  | 3000 |  | 3000 | Forest Trend |  | Meeting Minute, Workshop Report, SNU formation notification issued by sub region government | Improvemet of state and regional extractive sector governance | bar: 2020-07-20
|  | 8.2 Mon | Meeting, workshop |  | To make a bridge between the coordination of national and subnational units in Extractive Industry | Create the space to work out a deal on EITI related challengaes , advantages and conflicts in order to make improve | Improvement of EITI awareness and effective implementation of EITI in the sub-national level | MSG, NCS, MOBD, Sub-Region Government | [21 empty] | 1 | Times | 3000 | 3000 |  |  |  | 3000 |  | 3000 | Forest Trend |  | Meeting Minute, Workshop Report, SNU formation notification issued by sub region government | Improvemet of state and regional extractive sector governance | bar: 2020-07-20
|  | 8.3 Kayin | Meeting, workshop |  | To make a bridge between the coordination of national and subnational units in Extractive Industry | Create the space to work out a deal on EITI related challengaes , advantages and conflicts in order to make improve | Improvement of EITI awareness and effective implementation of EITI in the sub-national level | MSG, NCS, MOBD, Sub-Region Government | [21 empty] | 1 | Times | 3000 | 3000 |  | 3000 |  |  |  | 0 |  |  | Meeting Minute, Workshop Report, SNU formation notification issued by sub region government | Improvemet of state and regional extractive sector governance | bar: 2020-10-20
|  | 8.4 Kayah,Ayearwaddy, Chin , Yangon, Bago SNU formation | [27 empty] | 8 | Times | 3500 | 28000 | [5 empty] | 28000 | bar: 2020-08-20 to 2020-09-20; 2020-11-20 to 2021-02-21; 2021-05-21 to 2021-06-21
|  | 8.5 Coordination between MSG and SNU | MSG members attending to SNU meeting |  | To make a bridge between the coordination of national and subnational units in Extractive Industry | Create the space to work out a deal on EITI related challengaes , advantages and conflicts in order to make improve | Improvement of EITI awareness and effective implementation of EITI in the sub-national level | MSG, NCS, MOBD, Sub-Region Government | [21 empty] | 7 | Times | 600 | 4200 |  | 1200 |  |  |  | 3000 | bar: 2020-04-20; 2020-06-20 to 2020-07-20; 2020-09-20; 2020-11-20; 2021-01-21; 2021-03-21
9 | Mining Cadastre | [28 empty] | 0 | [8 empty] | 0
|  | 9.1 Mineral and Gemstone Casdastre Phase II consultant | Consultant | Objective 3 : To support implementation of sustainable development and natural resource governance reforms through the successful execution of EITI. | To pave the way to transparency in licening process of Mining sector ( Gems, Other minerals) | Uniform process to issue license from departments under MONREC | Reduce the overlapping of geological data, imporve transperncy in licensing process and attract the foreign investor | Consultant | [21 empty] | 1 | Times | 670000 | 670000 | 670000 |  |  |  |  | 0 |  |  | Office and furniture establishment , TOR and contract for the consultant, Cadaster Design, Deliverables by TOR of Phase II Consultant, Evaluation Report, Number of trainings, Installed equipments | Accuate regulations to issue licnese | bar: 2020-12-20
10 | MSG and sub-committee meeting | [37 empty] | 0
|  | 10.1 MSG meeting | Meeting | Objective 2 : To create an enabling environment for the effective implementation of the EITI standard. | To enable enviroment for sound policies on natural resource governance as a result of sustained dialogue among stakeholders | Luminous decision can make smooth the EITI process implemented by NCS, approval on the report | Improving the oversight implementation of EITI process and developing ahead of implementing corretive actions and 2nd validation process | MSG, NCS, MOBD |  |  | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20 | Meetings | 4000 | 80000 | 3000 | 8000 |  |  |  | 69000 |  |  | Meeting decisions, Meeting minutes approved, Number of participants | Strengthen the extractive government overseeing the EITI implementation, sustainable development process of Myanmar | 3.5 million budget
|  | 10.2 Sub-committee meeting | Meeting |  | To enable enviroment for sound policies on natural resource governance as a result of sustained dialogue among stakeholders | Luminous decision can make smooth the EITI process implemented by NCS, approval on the report, | Improving the oversight implementation of EITI process and developing ahead of implementing corretive actions and 2nd validation process | MSG, NCS, MOBD |  | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 79 | Meetings | 350 | 27650 | 3385 | 3500 |  |  |  | 20765 |  |  | Meeting decisions, Meeting minutes approved, Number of participants | Strengthen the extractive government overseeing the EITI implementation, sustainable development process of Myanmar | 3.5 million budget
11 | HR, Operation and Office Administration | [37 empty] | 0
|  | 11.1 MOBD Operational Cost | MOBD Staff travel and office supplies | [26 empty] | 6 | Months | 1000 | 6000 | 94494 |  |  |  |  | 6000 | bar: 2020-01-01 to 2021-09-21
|  | 11.2 NCS Operation Cost-Salaries | NCS Staff Salaries | [26 empty] | 12 | Months | 20102 | 241224 | 110439 |  |  |  |  | 241224 | bar: 2020-01-01 to 2021-09-21
|  | 11.3 NCS Opearation Cost | NCS Overhead ( Utilities, Travel, Communication service, Maintenance, Stationary, consumable material and other) | [26 empty] | 12 | Months | 4000 | 48000 | 36488 |  |  |  |  | 48000 | bar: 2020-01-01 to 2021-09-21
|  | 11.4 NCS Operation Cost - Rent | NCS Office Rental | [26 empty] | 1 | Year | 33600 | 33600 | [5 empty] | 33600 | bar: 2020-10-20
|  | 11.5 Fund raising - Advocacy | Contribution to EITI | [26 empty] | 0 | Year |  | 0 | [5 empty] | 0 |  |  |  |  | It is the amount that government should contribute.
|  | 11.6 Capcity Development - Study Tour | MSG study tour | [26 empty] | 1 |  | 269 | 269 | [5 empty] | 269 | bar: 2021-03-21
| TOTAL | [31 empty] | 2037968 | 1173369 | 179200 | 10000 | 11000 |  | 916820
916820
664399
252421
[36 empty] | -252421 |  | -267051
1387930
916580
2304510
5
5
5
5
5

## WB_NRGI_FT_Nat-Comine_Budget
MYANMAR EITI PROJECT PHASE II
3-YEAR MASTER PLAN & BUDGET (2017-2019)
Strategic Goals: To promote transparency and accountability in the extractive industries and material revenue management of the Union of Myanmar. (in line with the National Economic Policy 1 and 2, laid down by the Republic of the Union of Myanmar)
Activity No. | Category of Activity | Activities | WB 3.5 million Fund(2-6-2020) | Nathan Fund | NRGI Fund | Forest Trend Fund
1.1 | Communication and Outreach
1.1.1 | MEITI Report Print , 4th Report | Report Print and Translation | 7500
| MEITI Report Print , 5th Report | Report Print and Translation |  | 12000
1.1.3 | MEITI Report Launch Events for 4th Report | Media including TV, Radio, events and activities includign press release | 5000
| MEITI Report Launch Public and Debate Events for 5th Report | Media including TV, Radio, events and activities includign press release |  | 5000
| 5th MEITI Report Press conference | Media including TV, Radio, events and activities includign press release |  | 3000
1.1.4 | Forestry Report Launch Events etc | Media including TV, Radio, events and activities includign press release
1.1.5 | Public Debates | Public Gathering/Debate and Road Show
1.1.6 | Prints and Publication | Other prints and IEC material development | 3660
1.1.7a. | Website | Redesign, regular update and maintenance MEITI Website & on-line library | 1500
1.1.7b. | Video Production and Broadcasting | Video Production and Broadcasting
1.1.8 | Web-portal and Infographic | Open data, Inforgraphic and updated data | 3000
1.1.10 | National EITI Conference | National EITI Conference
Sub Total 1
Objective 2: To create an enabling environment for the effective implementation of the EITI Standard
2.1 | HR, Operation and Office Administration
2.1.1 | MOBD Operational Cost (6760) is MOBD-2 | MOBD Staff travel and Office Supplies | 94494
2.1.2 | NCS Operation Cost -Salaries | NCS Staff Salaries | 110439
2.1.3a | NCS Operation Cost | NCS Overheads ( Utilities, Travel, Communication service, Maintenance, Stationary, consumable material and other miscellaneous) | 36488
2.1.3b. | Consultant support service | Additional Travel and Accommodation costs to support consultants (BO, Cadastre etc)
2.1.4 | NCS Operation Cost - Rent | NCS Office Rental
2.1.5 | Office Set Up Cost | Equipment and Furniture
2.1.6 | Fund raising- Advocacy | Secure increased government contribution to EITI
2.1.7 | MSG Meeting | MSG Meeting | 3000 | 8000
2.1.8 | Sub-committee Meeting | MSG Sub-Committee Meetings | 3385 | 3500
2.1.8 a | Work Plan Review Workshop
2.1.8 b | EITI Awareness Meeting
2.1.9 | Translation Fee for related documents
Sub Total 2.1
2.2 | Workplan and Governance (APR, M&E- Review workshops)
2.2.1 | M&E Workshop | Review of annual progress (workplan), produce annual activity/progress report.
2.2.4 | Implementation of EITI report Recommendations Workshop | Workshop to develop the workplan for implementation of EITI recommendations
2.2.5 | MSG Governance Review Workshop | MSG Reform and Selection
2.2.5 a | EITI Restructure Review | Implementation of EITI restructuring |  | 31500
2.2.6 | SOE Reform Workshop | SOE workshop, Pre-meeting on SOE situations and future reform plans for extractor sector | 3883 |  |  | 5000
2.2.7 | Validation | Data Collection and Stakeholder Consultation workshops for initial assessment /Validation Group Meeting and Consultation Meeting for 12 Correction Action | 4200
2.2.8 | Validation | Contribution to International Secretariat
Sub Total 2.2
2.3 | Sub-National Coordination Unit (Formation and Functioning)
2.3.1 | SNU Formation and Coordination | Establishing Sub-National Coordination Units at State and Division level and further coordination with Union EITI.
|  | Kayin State |  | 3000
|  | Kayah and Mon State |  |  |  | 6000
2.3.2 | Coordination between MSG and SNUs | Review and evaluate reports from SNUs and determine coordinate consistent response to issues raised. MSG to establish internal monitoring and evaluation mechanism on workplan implementation?? |  | 1200
Sub Total 2.3
Sub Total 2
Objective 3:To support implementation of sustainable development and natural resource governance reforms through the successful execution of EITI.
3.1 | Technical and Reporting (IA main report, Forestry, BO, Mining Cadaster, SOE, Review of Artisenal Mining, Fasibility studies, Sub-national study, Implementation of recommendations, & other technical studies)
3.1.1 | Legislative institutionalization | Research to recommend legal options to EITI institunalization. Developing a draft EITI Law or amemdments to Sectoral Laws
3.1.3 | EITI Reconciliation Report 2 &3
3.1.3 | EITI Reconciliation Report 4
3.1.3 | EITI Reconciliation Report 5 | Independent Administrator and procure firm each year for the annual report (including scoping study) | 222276
3.1.3 | EITI Reconciliation Report 5
3.1.3 | EITI Reconciliation Report 6
3.1.3 b | EITI Reconciliation Report Workshops | Report reconciliation and Reporting entities workshops-Main IA
3.1.3 c | EITI Report Template Training | Template Training with IA and respective Agency | 1044
3.1.4 a | Forestry Reconciliation Report-1 | IA - First report
3.1.4 b | Forestry Reconciliation Report-2 | IA - First report
3.1.4 c | Forestry Reconciliation Report Workshops | Reporting entities workshops-Forestry IA
3.1.4 d | Hydro Reconcillation Report | Independent Administrator and procure firm each year for the annual report (including scoping study)
Hydro Reconcillation Report Meetings
3.1.5 | Mineral and Gemstone Cadaster Phase 1 Consultant | Design Phase
3.1.6 a | Mineral and Gemstone Pre-Cadastre Consultant | Pre-cadaster Working Group Consultant
3.1.6 b | Office Set Up Equipment for Pre Cadaster Working
3.1.6 c | Office Set up-Furniture for Pre-Cadastre working group
3.1.6 d | ARC,GIS Software
3.1.6 e | Maps, Stationery
Gemstone Mapping Consultant
3.1.7 | Mineral and Gemstone Cadaster Phase 2 Consultant | Development and installation of cadaster. | 670000
3.1.8 | Mineral and Gemstone Cadaster Equipment | Purchase of IT equipment and furniture
3.1.11a. | Beneficial Ownership (ASI) | Development of Workplan, Communicaiton Plan, Capacity Building Plan and Pilot Project
3.1.11b. | Beneficial Ownership (Matheiu) | BO Template
3.1.12 | Beneficial Ownership Meetings | BO workshops and Taskforce Meetings/ Template Training/ BO Press Condference | 3500
3.1.12 a | Beneficial Ownership
3.1.12 c | Beneficial Ownership (Online Disclosure Form) | Development of Beneficial Ownership discloure Online system |  | 50000
| BO Legal Review | Hire Consultant for legal analysis in BO |  | 20000
3.1.14a. | Systematic Disclosure Feasibility Study | Hire Consultant to conduct Systematic Disclosure and mainsterming |  | 40000
| Systematic Disclosure Consultaing | Workshop to develop Systematic Disclosure and mainstreaming |  | 1000
3.1.4b | Systematic Disclosure Consultancy
| Contract Transparency | Workshop and development for contract transparency workplan |  |  | 10000
| Project level Reporting | Workshop on Project Level Reporting |  | 1000
Sub Total 3.1
3.2 | Training and Capacity Development (Capacity Development for 3 MSG entities, MOBD, NCS & SNU capacity building)
3.2.1 a | Capacity Development | Implement Capacicty Development Plan (MSG, Private Sector, Governemnt, CSO, Media, EAOs, MOBD, NCS, Parliament and others)
3.2.1 b | Capacity Development for Awareness | EITI Standard Awareness
3.2.2 | Corrective Action Planning and Workshop | Corrective Actions and recommendation, SOE workshop, follow up action
3.2.3 | Capacity Development- Study Tour | MSG Study Tours
3.2.4 | Capacity Development- Int'l EITI events | EITI Global/ Regional Conferences and Board Meetings
3.2.5 | Financial Management Training (MOBD/NCS) | MOBD Financial management capacity development
TOTAL |  |  | 1173369 | 179200 | 10000 | 11000
Note on B74: To be funded from the 500 K Cost Exptension

## MDTF_Balance_Workplan 29-5-20
MYANMAR EITI PROJECT PHASE II
3-YEAR MASTER PLAN & BUDGET (2017-2021)
Strategic Goals: To promote transparency and accountability in the extractive industries and material revenue management of the Union of Myanmar. (in line with the National Economic Policy 1 and 2, laid down by the Republic of the Union of Myanmar)
Activity No. | Category of Activity | Activities | Implementing Agency | Category of Expense | Outputs | KPI | TOTAL BUDGET WB 3.5 MUSD Grant | 2017 | Q-1'18 | Q-2'18 | Q-3'18 | Q-4'2018 | 2018 Total | Q -1,19 | Q -2,19 | July & August 2019 | Sept'19 | Q -3,19 | Oct'19 | Nov'19 | Dec'19 | Q -4,19 | 2019 Total | Jan'2020 | Feb'2020 | Mar'2020 | Q -1,2020 | Apr'2020 | May' 2020 | Up to 29 May 2020 | Budget for 3.5 Million USD Remainder (29-5-20) | Budget for 3.5 Million USD Remainder W&G Sub-Committee (13,14-2-2020) | Budget for 3.5 Million USD Remainder | Budget for 3.5 Million USD Remainder | Q4'19 | Q -1,20 | Q -2,20 | Q3'20 | Q4'20 | Q -1,21 | Up to 2021 March | Proposed Budget for 3.5 USD W&G Sub-Committee (2-6-2020)
[8 empty] | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Balance | Balance | Budget | Budget | Budget | Budget | Budget | Budget | Budget | Budget | Budget | Budget
1.1 | Communication and Outreach
1.1.1 | MEITI Report Print | Report Print |  | Goods | Printed copies of report (Executive Summary, Full Report, Myanmar Version, English Version) | No. of copies of each version printed No. of copies of each version distriubuted | 22928.557 | 0 | 0 | 0 | 12278.557 | 0 | 12278.557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 12278.557 | 10650 | 10650 | 10650 | 10650 |  | 10650 |  |  |  |  | 10650 | 7100 | Printing 2000, Translation 5100 | 3550
1.1.2 | Forestry Report Printing | Report Print | NCS Communication, Communication and Outreach Sub-Committee | Goods | Printed copy of Forestry Report (Myanmar and English version) | No. of copies of each version printed No. of copies of each version distriubuted | 7941 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7941 | 7941 |  |  |  | 0 | 7941 | 0 | 0 |  | 0 |  |  | 7941 | 0 | [9 empty] | 0
1.1.3 | MEITI Report Launch Events etc | Media including TV, Radio, events and activities includign press release | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased knowledge of EITI and extractives in Myanmar | No. of events, TV /Radio Programs/ Media Articles No. and details of participants and audiences (gender, geographical location, ethnicity etc) Event Reports / quaility (accuracy of media reports) | 28592.5841 | 0 | 0 | 0 | 1980.9173 | 123.6668 | 2104.5841 | 19387 | 2101 |  |  | 0 |  |  |  | 0 | 21488 | 0 | 0 |  | 0 |  |  | 23592.5841 | 5000 | 5000 | 5000 | 5000 |  | 2500 | 2500 |  |  |  | 5000 | 5000
1.1.4 | Forestry Report Launch Events etc | Media including TV, Radio, events and activities includign press release | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased knowledge of Forestry extractives in Myanmar | No. of events, TV /Radio Programs/ Media Articles No. and details of participants and audiences (gender, geographical location, ethnicity etc) Event Reports / quaility (accuracy of media reports) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
1.1.5 | Public Debates | Public Gathering/Debate and Road Show | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased knowledge of EITI and extractives in Myanmar | No. of public gatherings, debates, roadshow events No. and details of participants Event Feedback and Reports | 6815.1016 | 0 | 0 | 0 | 0 | 4062.1016 | 4062.1016 | 2753 |  |  |  | 0 |  |  |  | 0 | 2753 | 0 | 0 |  | 0 |  |  | 6815.1016 | 0 | [9 empty] | 0
1.1.6 | Prints and Publication | Other prints and IEC material development | NCS Communication, Communication and Outreach Sub-Committee | Goods | IEC Materials | No and type of materials produced No and type of materails distributed/ viewed online Feedback on materials (?) | 18866.3617 | 0 | 2706.2626 | 2736.0684 | 0 | 1230.0308 | 6672.3617 |  | 4964 | 1630 |  | 1630 |  |  |  | 0 | 6594 | 0 | 0 | 1538.9125 | 1538.9125 |  |  | 14805.2742 | 4061.0875 | 5600 | 5600 | 5600 |  | 5600 |  |  |  |  | 5600 | 4061 | Will remail 1761 after paid printing cost 2400
1.1.7a. | Website | Redesign, regular update and maintenance MEITI Website & on-line library | NCS Communication, Communication and Outreach Sub-Committee | Non Consulting Services | Website | No. of hits on website Feedback Survey Validation Comments | 5097.565 | 575.4544 | 1279.7946 | 0 | 2642.3161 |  | 3922.1106 |  |  |  |  | 0 | 442 |  |  | 442 | 442 | 0 | 9 |  | 9 |  |  | 4948.565 | 149 | 149 |  |  |  | 158 |  |  |  |  | 158 | 1500 | To add ammount after confirmed communication | 1351
1.1.7b. | Video Production and Broadcasting | Video Production and Broadcasting | NCS Communication, Communication and Outreach Sub-Committee | Non Consulting Services | Videos | Number of views, boradcasts, feedback | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
1.1.8 | Web-portal and Infographic | Open data, Inforgraphic and updated data | NCS Communication, Communication and Outreach Sub-Committee | Non Consulting/ Consulting | Infographics and open data pages | No. of users Feedback and Validation Comments | 3000 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 3000 | 3000 | 3000 |  |  | 3000 |  |  |  |  | 3000 | 3000
1.1.10 | National EITI Conference | National EITI Conference | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased understanding of MEITI Improved multistakeholder participation Documented assessment of progress, Input for planning | Event Report No. and details of participants Progress assessment and Planning input Feedback from participants | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
Sub Total 1 | [6 empty] | 93241.1694 | 575.4544 | 3986.0572 | 2736.0684 | 16901.7903 | 5415.7991 | 29039.715 | 22140 | 7065 | 1630 | 7941 | 9571 | 442 | 0 | 0 | 442 | 39218 | 0 | 9 | 1538.9125 | 1547.9125 | 0 | 0 | 70381.0819 | 22860.0875 | 24399 | 24250 | 21250 | 0 | 21908 | 2500 | 0 | 0 | 0 | 24408 | 20661
Objective 2: To create an enabling environment for the effective implementation of the EITI Standard
2.1 | HR, Operation and Office Administration
2.1.1 | MOBD Operational Cost | MOBD Staff travel and Office Supplies | MOBD | Operating Cost/ Goods | Project Financial Management, Procurement and Grant Compliance | FM reports to MSG and Donors, Procurement Plans and Documentation OAG Audit LC and WC Support to EITI process | 114623 | 2101 | 1543 | 1253 | 2683 | 1709 | 7188 | 1825 | 2342 | 1081.21 | 947 | 2028.21 | 469 | 320 | 790 | 1579 | 7774.21 | 708 | 655 | 1036.2241 | 2399.2241 | 196.5997 | 470.2462 | 20129.2801 | 94493.7199 | 96204 | 96859 | 96859 |  | 3000 | 3000 | 3000 | 22300 | 65559 | 96859 | 94548
2.1.2 | NCS Operation Cost -Salaries | NCS Staff Salaries | NCS | Operating Cost | Successful Implementation of Work Plan activities | APR EITI Reconciliation Reports MSG and Subcommittee Minutes Staff Performance Evaluations | 589182.106 | 43920.6314 | 65176.2842 | 13117.5879 | 71704.6044 | 13651.818 | 163650.2945 | 52516 | 34762 | 40605.18 | 26566 | 67171.18 |  | 15409 |  | 15409 | 169858.18 | 28386 | 15191 | 14858.737 | 58435.737 | 28811.2022 | 14067.5286 | 478743.5739 | 110438.5321 | 168176 | 168116 | 168116 |  | 42000 | 60000 | 66116 |  |  | 168116 | 109472 | Actual Cost up to May 15034
2.1.3a | NCS Operation Cost | NCS Overheads ( Utilities, Travel, Communication service, Maintenance, Stationary, consumable material and other miscellaneous) | NCS | Operating Cost | Successful Implementation of Work Plan activities | APR EITI Reconciliation Reports MSG and Subcommittee Minutes | 136625.3707 | 10438.0187 | 21284.5961 | 0 | 17263.446 | 0 | 38548.0421 | 14988 | 7041 | 7076.04 | 7238 | 14314.04 |  | 5213 |  | 5213 | 41556.04 | 5668 | 2239.27 | 1061.5865 | 8968.8565 | 386.5302 | 239.4874 | 100136.9748 | 36488.3959 | 38176 | 38658 | 38658 |  | 8475 | 12000 | 18183 |  |  | 38658 | 36433 | Actual Cost for May 295
2.1.3b. | Consultant support service | Additional Travel and Accommodation costs to support consultants (BO, Cadastre etc) | NCS | Operating Cost | Facilitation of Consultants' Work | Consultant Deliverables | 3215.3194 | 0 | 0 | 0 | 777.3194 | 0 | 777.3194 |  | 1650 |  | 788 | 788 |  |  |  | 0 | 2438 | 0 | 0 |  | 0 |  |  | 3215.3194 | 0 | [9 empty] | 0
2.1.4 | NCS Operation Cost - Rent | NCS Office Rental | NCS | Operating Cost | Office Space | Office Rental Contract and Payment Reciept | 88193.1054 | 9031.9439 | 12382.2615 | 0 | 36000.9 | 0 | 48383.1616 |  |  |  | 30778 | 30778 |  |  |  | 0 | 30778 | 0 | 0 |  | 0 |  |  | 88193.1054 | 0 |  |  | 0 | [6 empty] | 0
2.1.5 | Office Set Up Cost | Equipment and Furniture | NCS, MOBD | Goods | Furniture and Equipment | Purchase Receipts Procurement Report Inventory | 32492.7881 | 9958.6036 | 4526.1845 | 0 | 0 | 0 | 4526.1845 |  |  |  | 17677 | 17677 | 324 |  |  | 324 | 18001 | 0 | 7 |  | 7 |  |  | 32492.7881 | 0 | 0 |  | 0 | 0 | [5 empty] | 0
2.1.6 | Fund raising- Advocacy | Secure increased government contribution to EITI | MOBD, MSG | Non Consulting |  |  | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
2.1.7 | MSG Meeting | MSG Meeting | NCS | Workshop and Meeting | MSG Meeting Decisions and Outputs (approved TOR, reports etc) | Meeting Minutes Approved (Myanmar and English) Minutes posted on MEITI Website Funds Raised | 78709.2271 | 8192.0498 | 23326.0527 | 3048.5487 | 7020 | 3807.5759 | 37202.1773 | 6602 | 3376 | 6105 | 3598 | 9703 |  |  |  | 0 | 19681 | 7134 | 0 | 3636.7787 | 10770.7787 |  |  | 75846.0058 | 2863.2213 | 6500 | 6500 | 6500 |  |  | 6500 |  |  |  | 6500 | 3000 |  | 137
2.1.8 | Sub-committee Meeting | MSG Sub-Committee Meetings | NCS | Workshop and Meeting | Subcommittee Meeting Recommendations and Outputs (draft TOR, reports etc) | Meeting Minutes Approved (Myanmar and English)Minutes posted on MEITI Website Funds Raised | 24609.6681 | 3767.6924 | 2866.3571 | 2961.752 | 2398.335 | 2794.5316 | 11020.9757 | 2233 | 3108 | 732 | 713 | 1445 | 133 |  | 200 | 333 | 7119 | 0 | 218 | 979.5944 | 1197.5944 |  |  | 23105.2625 | 1504.4056 | 2484 | 2702 | 2702 |  | 1400 | 1302 |  |  |  | 2702 | 3385 |  | 1881
2.1.8 a | Work Plan Review Workshop | [5 empty] | 2400 | [9 empty] | 2400 | 2400 |  |  |  | 0 | 2400 | 0 | 0 |  | 0 |  |  | 2400 | 0 | [9 empty] | 0
2.1.8 b | EITI Awareness Meeting | [5 empty] | 537 | [9 empty] | 537 | 537 |  |  |  | 0 | 537 | 0 | 0 |  | 0 |  |  | 537 | 0 | [9 empty] | 0
2.1.9 | Translation Fee for related documents | [5 empty] | 15493 | 2515 | 3691 | 1066 | 461 | 0 | 5218 | 3603 | 810 | 232 |  | 232 | 3115 |  |  | 3115 | 7760 | 0 | 0 |  | 0 |  |  | 15493 | 0 | [9 empty] | 0
Sub Total 2.1 | [6 empty] | 1086080.5849 | 89924.9397 | 134795.7361 | 21446.8887 | 138308.6048 | 21962.9256 | 316514.1552 | 81767 | 53089 | 55831.43 | 91242 | 147073.43 | 4041 | 20942 | 990 | 25973 | 307902.43 | 41896 | 18310.27 | 21572.9208 | 81779.1908 | 29394.3321 | 14777.2623 | 840292.31 | 245788.2748 | 311540 | 312835 | 312835 | 0 | 54875 | 82802 | 87299 | 22300 | 65559 | 312835 | 246838
2.2 | Workplan and Governance (APR, M&E- Review workshops)
2.2.1 | M&E Workshop | Review of annual progress (workplan), produce annual activity/progress report. | NCS, MSG | Workshop and Meeting | Increased understanding of MEITI Improved multistakeholder participation Documented assessment of progress, Input for planning | Event Report No. and details of participants Progress assessment and Planning input Feedback from participants | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
2.2.4 | Implementation of EITI report Recommendations Workshop | Workshop to develop the workplan for implementation of EITI recommendations | MOBD, NCS, Subcommittee, MSG | Workshop and meeting | Systematic assessment of EITI Recommendations from reports and planning for their implementation | SMART Work Plan for implementation Recommendations | 2444.3111 | 0 | 0 | 0 | 2444.3111 | 0 | 2444.3111 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 2444.3111 | 0 | [9 empty] | 0
2.2.5 | MSG Governance Review Workshop | MSG Reform and Selection | NCS, MSG, Government Agencies | Workshop and meeting/ Consultancy/ Goods | Outputs according to the agreed work plan | Indicators according to the agreed work plan | 5238 | 0 | 3224 | 0 | 0 | 0 | 3224 |  | 2014 |  |  | 0 |  |  |  | 0 | 2014 | 0 | 0 |  | 0 |  |  | 5238 | 0 | [9 empty] | 0
2.2.5 a | EITI Restructure Review | Implementation of EITI restructuring | MOBD, NCS, Subcommittee, MSG, Government Agencies | Workshop and meeting/ Consultancy/ Goods |  |  | 0 | [10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
2.2.6 | SOE Reform Workshop | SOE workshop, Pre-meeting on SOE situations and future reform plans for extractor sector | MOBD, NCS, Subcommittee, MSG | Workshop and Meeting | Increased awareness of MEITI Report recommendtions on SOE Reform Documented multi-stakeholder review of current SOE reform plans, achievements and challenges Plans for ongoing reforms and their coordination with MEITI | Workshop Report incl participation Documentation of assessments, decisions and plans | 12115 | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 5456 |  | 1222 | 1222 |  | 1284 |  | 1284 | 8232 | 0 | 0 |  | 0 |  |  | 8232 | 3883 | 3883 | 3883 | 3883 |  |  | 3883 |  |  |  | 3883 | 3883
2.2.7 | Validation | Data Collection and Stakeholder Consultation workshops for initial assessment /Validation Group Meeting and Consultation Meeting for 12 Correction Action | NCS, MSG | Workshop and meeting | Multistakeholder assessment and documentation of MEITI process Capacity Building for MEITI Stakeholders | Validation Report | 9487.9419 | 0 | 0 | 0 | 2957.9419 | 0 | 2957.9419 | 2330 |  |  |  | 0 |  |  |  | 0 | 2330 | 0 | 0 |  | 0 |  |  | 5287.9419 | 4200 | 4200 | 4200 | 4200 |  | 1050 | 1050 | 1050 | 1050 |  | 4200 | 4200
2.2.8 | Validation | Contribution to International Secretariat | MOBD, NCS |  | Payment made | Money transfer receipt, Bank Transaction Sheet, letter of acknowledgement from EITI | 10000 | 0 | 0 | 0 | 0 | 10000 | 10000 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 10000 | 0 | [9 empty] | 0
Sub Total 2.2 | [6 empty] | 39285.2531 | 0 | 3224 | 0 | 5402.2531 | 10000 | 18626.2531 | 2600 | 7470 | 0 | 1222 | 1222 | 0 | 1284 | 0 | 1284 | 12576 | 0 | 0 | 0 | 0 | 0 | 0 | 31202.2531 | 8083 | 8083 | 8083 | 8083 | 0 | 1050 | 4933 | 1050 | 1050 | 0 | 8083 | 8083
2.3 | Sub-National Coordination Unit (Formation and Functioning)
2.3.1 | SNU Formation and Coordination | Establishing Sub-National Coordination Units at State and Division level and further coordination with Union EITI. | NCS, MSG, Communication Officer | Workshop and meeting | SNUs Formed (Membership, TOR) Meeting Records / Minutes/ Reports | No. of SNUs Formed SNU Membership details (inclusivity, participation, geographic coverage) SNU TORs and Work Plans | 34749.2633 | 0 | 10632.5588 | 0 | 10549.19 | 3180.5145 | 24362.2633 | 10387 |  |  |  | 0 |  |  |  | 0 | 10387 | 0 | 0 |  | 0 |  |  | 34749.2633 | 0 | [9 empty] | 0
2.3.2 | Coordination between MSG and SNUs | Review and evaluate reports from SNUs and determine coordinate consistent response to issues raised. MSG to establish internal monitoring and evaluation mechanism on workplan implementation?? | NCS, MSG, SNU |  | ??? | ??? | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
Sub Total 2.3 | [6 empty] | 34749.2633 | 0 | 10632.5588 | 0 | 10549.19 | 3180.5145 | 24362.2633 | 10387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10387 | 0 | 0 | 0 | 0 | 0 | 0 | 34749.2633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total 2 |  |  |  | Sub Total 2 |  |  | 1160115.1012 | 89924.9397 | 148652.2949 | 21446.8887 | 154260.0478 | 35143.4401 | 359502.6715 | 94754 | 60559 | 55831.43 | 92464 | 148295.43 | 4041 | 22226 | 990 | 27257 | 330865.43 | 41896 | 18310.27 | 21572.9208 | 81779.1908 | 29394.3321 | 14777.2623 | 906243.8264 | 253871.2748 | 319623 | 320918 | 320918 | 0 | 55925 | 87735 | 88349 | 23350 | 65559 | 320918 | 254921
Objective 3:To support implementation of sustainable development and natural resource governance reforms through the successful execution of EITI.
3.1 | Technical and Reporting (IA main report, Forestry, BO, Mining Cadaster, SOE, Review of Artisenal Mining, Fasibility studies, Sub-national study, Implementation of recommendations, & other technical studies)
3.1.1 | Legislative institutionalization | Research to recommend legal options to EITI institunalization. Developing a draft EITI Law or amemdments to Sectoral Laws | NCS, Subcommittee, MSG | Consultancy | Research Report and Recommendations | Research Report and Recommendations accpeted by MSG | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.3 | EITI Reconciliation Report 2 &3 | [5 empty] | 270890 | 110740 | 83055 | 0 | 0 | 0 | 83055 | 77095 |  |  |  | 0 |  |  |  | 0 | 77095 | 0 | 0 |  | 0 |  |  | 270890 | 0 | [9 empty] | 0
3.1.3 | EITI Reconciliation Report 4 | [5 empty] | 248084 |  | 0 | 0 | 0 | 0 | 0 |  | 173898 | 74186 |  | 74186 |  |  |  | 0 | 248084 | 0 | 0 |  | 0 |  |  | 248084 | 0 | [9 empty] | 0
3.1.3 | EITI Reconciliation Report 5 | Independent Administrator and procure firm each year for the annual report (including scoping study) | MOBD, NCS, IA | Consulting | EITI Reconciliation Reports | Reports produced by deadline Reports approved by MSG Validation results on EITI Standard 2-6 | 370460 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 148184 |  | 148184 | 222276 | 370460 | 370460 | 370460 |  | 370460 |  |  |  |  | 370460 | 222276
3.1.3 | EITI Reconciliation Report 5 | [5 empty] | 0 | [10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.3 | EITI Reconciliation Report 6 | [5 empty] | 0 | [10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.3 b | EITI Reconciliation Report Workshops | Report reconciliation and Reporting entities workshops-Main IA |  |  |  |  | 21543.4513 | 4439.4513 | 10484 | 0 | 0 | 0 | 10484 | 4744 | 1876 |  |  | 0 |  |  |  | 0 | 6620 | 0 | 0 |  | 0 |  |  | 21543.4513 | 0 | [9 empty] | 0
3.1.3 c | EITI Report Template Training | Template Training with IA and respective Agency |  |  |  |  | 7113 | [10 empty] | 0 |  |  | 140 | 140 | 140 | 3764 | 2165 |  | 5929 |  |  | 6069 | 1044 | 1044 | [8 empty] | 0 | 1044
3.1.4 a | Forestry Reconciliation Report-1 | IA - First report |  | Consulting | Forestry Reconconciliation Report(s) | Report(s) approved by MSG | 160000 | 0 | 48000 | 80000 | 0 | 0 | 128000 |  |  | 32000 |  | 32000 |  |  |  | 0 | 32000 | 0 | 0 |  | 0 |  |  | 160000 | 0 | [9 empty] | 0
3.1.4 b | Forestry Reconciliation Report-2 | IA - First report |  |  |  |  | 0 | 0 |  |  | 0 | 0 | [5 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.4 c | Forestry Reconciliation Report Workshops | Reporting entities workshops-Forestry IA |  |  |  |  | 3952.4048 | 0 | 3952.4048 | 0 | 0 | 0 | 3952.4048 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 3952.4048 | 0 | [9 empty] | 0
3.1.4 d | Hydro Reconcillation Report | Independent Administrator and procure firm each year for the annual report (including scoping study) |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
| Hydro Reconcillation Report Meetings | [5 empty] | 223 |  | 0 | 0 | 0 | 0 | 0 | 223 |  |  |  | 0 |  |  |  | 0 | 223 | 0 | 0 |  | 0 |  |  | 223 | 0 | [9 empty] | 0
3.1.5 | Mineral and Gemstone Cadaster Phase 1 Consultant | Design Phase | MONREC, NCS, Subcommitte, MSG | Consulting | Preliminary, Intermediate and Final Report Mineral Cadastre Conceptual Design TOR for Phase 2 | Documents received and approved by MONREC and MSG | 119125.15 | 40017 | 40024 | 0 | 39084.15 | 0 | 79108.15 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 119125.15 | 0 | [9 empty] | 0
3.1.6 a | Mineral and Gemstone Pre-Cadastre Consultant | Pre-cadaster Working Group Consultant | MONREC, NCS, Subcommitte, MSG | Consulting | Training and on the job support Precadastre developed | No. of staff trained No. of Training Hours completed Completeness of Precadastre | 41390 | 0 | 0 | 0 | 12600 | 0 | 12600 | 15000 |  | 13790 |  | 13790 |  |  |  | 0 | 28790 | 0 | 0 |  | 0 |  |  | 41390 | 0 | [9 empty] | 0
3.1.6 b | Office Set Up Equipment for Pre Cadaster Working | [5 empty] | 21980.74 | 0 | 0 | 0 | 0 | 18168.74 | 18168.74 |  | 983 | 2771 | 58 | 2829 |  |  |  | 0 | 3812 | 0 | 0 |  | 0 |  |  | 21980.74 | 0 | [9 empty] | 0
3.1.6 c | Office Set up-Furniture for Pre-Cadastre working group | [5 empty] | 5632.769 | 0 | 0 | 0 | 0 | 3259.769 | 3259.769 |  | 2373 |  |  | 0 |  |  |  | 0 | 2373 | 0 | 0 |  | 0 |  |  | 5632.769 | 0 | [9 empty] | 0
3.1.6 d | ARC,GIS Software | [5 empty] | 40000 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 40000 | 0 |  | 40000 |  |  | 40000 | 0 | [9 empty] | 0
3.1.6 e | Maps, Stationery | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
| Gemstone Mapping Consultant | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.7 | Mineral and Gemstone Cadaster Phase 2 Consultant | Development and installation of cadaster. | MONREC, NCS, Subcommitte, MSG | Consulting | Deliverables outlined in TOR for Phase 2 | Indicators according to deliverables from TOR Phase 2 | 670000 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 670000 | 670000 | 670000 | 670000 |  | 134000 | 134000 | 134000 | 134000 | 134000 | 670000 | 670000
3.1.8 | Mineral and Gemstone Cadaster Equipment | Purchase of IT equipment and furniture | MONREC, NCS, MOBD | Goods | Equipment and Furniture | Procurement report Purchase Receipt Inventory | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.11a. | Beneficial Ownership (ASI) | Development of Workplan, Communicaiton Plan, Capacity Building Plan and Pilot Project | NCS, Subcommittee, MSG | Consultancy | BO Work Plan, BO Communications Plan, BO Capacity Development Plan, BO Pilot Project | Deliverables approved by MSG | 120000 | 0 | 36000 | 0 | 0 | 84000 | 120000 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 120000 | 0 | [9 empty] | 0
3.1.11b. | Beneficial Ownership (Matheiu) | BO Template |  |  |  |  | 5685 | [9 empty] | 5685 | 5685 |  |  |  | 0 | 5685 | 0 | 0 |  | 0 |  |  | 5685 | 0
3.1.12 | Beneficial Ownership Meetings | BO workshops and Taskforce Meetings/ Template Training/ BO Press Condference | NCS, Task Force | Meeting and Workshop |  | No. of workshop/ meeting | 23824.3925 | 0 | 0 | 3657.1034 | 2001.05 | 6301.239 | 11959.3925 | 898 |  | 3260 | 2205 | 5465 |  |  |  | 0 | 6363 | 1002 | 0 | 1688.9575 | 2690.9575 |  |  | 21013.35 | 2811.0425 | 4500 | 4500 |  |  | 4500 |  |  |  |  | 4500 | 3500 |  | 689
3.1.12 a | Beneficial Ownership | [5 empty] | 6525 | [9 empty] | 5998 | 5998 |  |  | 527 | 527 | 6525 | 0 | 0 |  | 0 |  |  | 6525 | 0 | [9 empty] | 0
3.1.12 c | Beneficial Ownership (Online Disclosure Form) | Development of Beneficial Ownership discloure Online system | DICA | Non Consulting Services |  |  | 8000 | [10 empty] | 0 |  |  | 7607 | 7607 | 7607 | 0 | 155 |  | 155 |  |  | 7762 | 238 | 238 |  |  |  | 393 |  |  |  |  | 393 | 0 | Reduce as no activity | 238
3.1.14a. | Systematic Disclosure Feasibility Study | [5 empty] | 0 | [10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.4b | Systematic Disclosure Consultancy | [5 empty] | 0 | [10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
Sub Total 3.1 | [6 empty] | 2144428.9075 | 155196.4513 | 221515.4048 | 83657.1034 | 53685.2 | 111729.748 | 470587.4562 | 97960 | 179130 | 126007 | 13946 | 139953 | 0 | 0 | 8274 | 8274 | 425317 | 44766 | 2320 | 1688.9575 | 48774.9575 | 148184 | 0 | 1248059.865 | 896369.0425 | 1046242 | 1044960 | 1040460 | 0 | 509353 | 134000 | 134000 | 134000 | 134000 | 1045353 | 896820
3.2 | Training and Capacity Development (Capacity Development for 3 MSG entities, MOBD, NCS & SNU capacity building)
3.2.1 a | Capacity Development | Implement Capacicty Development Plan (MSG, Private Sector, Governemnt, CSO, Media, EAOs, MOBD, NCS, Parliament and others) | NCS, MSG | Meeting and Workshop | Outputs defined in capacity development plan | Indicators defined in Capacity Development Plan Incld No. of participants, participant criteria (gender, stakeholder group, geographic location etc) Participant feedback | 33729.5837 | 8267.6968 | 4147.6666 | 720.018 | 11964.2991 | 8629.9032 | 25461.8869 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 33729.5837 | 0 | [9 empty] | 0
3.2.1 b | Capacity Development for Awareness | EITI Standard Awareness |  | Workshop and meeting/ Consultancy/ Goods |  |  | 0 | [10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.2.2 | Corrective Action Planning and Workshop | Corrective Actions and recommendation, SOE workshop, follow up action | NCS, Subcommittee, MSG | Workshop and meeting/ Consultancy/ Goods |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.2.3 | Capacity Development- Study Tour | MSG Study Tours | MSG | Non Consulting | Outputs defined in Study Tour Concept Note or Plan | Indicators from concpet note or plan Incld No. of participants, participant criteria (gender, stakeholder group, geographic location etc) Participant feedback and cascading activities | 24584.7365 | 0 | 0 | 0 | 12702.7365 | 0 | 12702.7365 |  | 567 |  | 11046 | 11046 |  |  |  | 0 | 11613 | 0 | 0 |  | 0 |  |  | 24315.7365 | 269 | 269 | 269 |  |  | 269 |  |  |  |  | 269 | 0 | Reduce as no activity | 269
3.2.4 | Capacity Development- Int'l EITI events | EITI Global/ Regional Conferences and Board Meetings | MSG | Non Consulting | EITI Internnational Events attended | No. of events attended, No. of participants, cascade activities | 13380 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 12256 | 1124 | 13380 |  |  |  | 0 | 13380 | 0 | 0 |  | 0 |  |  | 13380 | 0 | [9 empty] | 0
3.2.5 | Financial Management Training (MOBD/NCS) | MOBD Financial management capacity development | NCS, Subcommittee, MSG | Consulting | Training and on the job support | No. of MOBD staff trained | 30520.8979 | 0 | 5969.7164 | 0 | 9261.1815 | 0 | 15230.8979 |  |  |  | 15290 | 15290 |  |  |  | 0 | 15290 | 0 | 0 |  | 0 |  |  | 30520.8979 | 0 | [9 empty] | 0
Sub Total 3.2 | [6 empty] | 102215.2181 | 8267.6968 | 10117.383 | 720.018 | 33928.2171 | 8629.9032 | 53395.5213 | 0 | 567 | 12256 | 27460 | 39716 | 0 | 0 | 0 | 0 | 40283 | 0 | 0 | 0 | 0 | 0 | 0 | 101946.2181 | 269 | 269 | 269 | 0 | 0 | 269 | 0 | 0 | 0 | 0 | 269 | 0
Sub Total 3 |  |  |  | Sub Total 3 |  |  | 2246644.1256 | 163464.1481 | 231632.7878 | 84377.1214 | 87613.4171 | 120359.6512 | 523982.9775 | 97960 | 179697 | 138263 | 41406 | 179669 | 0 | 0 | 8274 | 8274 | 465600 | 44766 | 2320 | 1688.9575 | 48774.9575 | 148184 | 0 | 1350006.0831 | 896638.0425 | 1046511 | 1045229 | 1040460 | 0 | 509622 | 134000 | 134000 | 134000 | 134000 | 1045622 | 896820
GRAND TOTAL |  |  |  | Grand Total |  |  | 3500000.3962 | 253964.5421 | 384271.1398 | 108560.0785 | 258775.2552 | 160918.8905 | 912525.364 | 214854 | 247321 | 195724.43 | 141811 | 337535.43 | 4483 | 22226 | 9264 | 35973 | 835683.43 | 86662 | 20639.27 | 24800.7907 | 132102.0607 | 177578.3321 | 14777.2623 | 2326630.9913 | 1173369.4049 | 1390533 | 1390397 | 1382628 | 0 | 587455 | 224235 | 222349 | 157350 | 199559 | 1390948 | 1172402 |  | 967.4049
| TOTAL (July 2019 to 13th May 2020) | [16 empty] | 697966.0851
Note on B70: To be funded from the 500 K Cost Exptension

## Proposed_Revised(2-6-20WPG)
MYANMAR EITI PROJECT PHASE II
3-YEAR MASTER PLAN & BUDGET (2017-2021)
Strategic Goals: To promote transparency and accountability in the extractive industries and material revenue management of the Union of Myanmar. (in line with the National Economic Policy 1 and 2, laid down by the Republic of the Union of Myanmar)
Activity No. | Category of Activity | Activities | Implementing Agency | Category of Expense | Outputs | KPI | TOTAL BUDGET WB 3.5 MUSD Grant | 2017 | Q-1'18 | Q-2'18 | Q-3'18 | Q-4'2018 | 2018 Total | Q -1,19 | Q -2,19 | July & August 2019 | Sept'19 | Q -3,19 | Oct'19 | Nov'19 | Dec'19 | Q -4,19 | 2019 Total | Jan'2020 | Feb'2020 | Mar'2020 | Q -1,2020 | Apr'2020 | May' 2020 | Up to 29 May 2020 | Budget for 3.5 Million USD Remainder (29-5-20) | Budget for 3.5 Million USD Remainder W&G Sub-Committee (13,14-2-2020) | Budget for 3.5 Million USD Remainder | Budget for 3.5 Million USD Remainder | Q4'19 | Q -1,20 | Q -2,20 | Q3'20 | Q4'20 | Q -1,21 | Up to 2021 March | Proposed Budget for 3.5 USD W&G Sub-Committee (2-6-2020)
[8 empty] | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Balance | Balance | Budget | Budget | Budget | Budget | Budget | Budget | Budget | Budget | Budget | Budget
1.1 | Communication and Outreach
1.1.1 | MEITI Report Print | Report Print |  | Goods | Printed copies of report (Executive Summary, Full Report, Myanmar Version, English Version) | No. of copies of each version printed No. of copies of each version distriubuted | 22928.557 | 0 | 0 | 0 | 12278.557 | 0 | 12278.557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 12278.557 | 10650 | 10650 | 10650 | 10650 |  | 10650 |  |  |  |  | 10650 | 7500 | Printing 2400, Translation 5100 | 3150
1.1.2 | Forestry Report Printing | Report Print | NCS Communication, Communication and Outreach Sub-Committee | Goods | Printed copy of Forestry Report (Myanmar and English version) | No. of copies of each version printed No. of copies of each version distriubuted | 7941 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7941 | 7941 |  |  |  | 0 | 7941 | 0 | 0 |  | 0 |  |  | 7941 | 0 | [9 empty] | 0
1.1.3 | MEITI Report Launch Events etc | Media including TV, Radio, events and activities includign press release | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased knowledge of EITI and extractives in Myanmar | No. of events, TV /Radio Programs/ Media Articles No. and details of participants and audiences (gender, geographical location, ethnicity etc) Event Reports / quaility (accuracy of media reports) | 28592.5841 | 0 | 0 | 0 | 1980.9173 | 123.6668 | 2104.5841 | 19387 | 2101 |  |  | 0 |  |  |  | 0 | 21488 | 0 | 0 |  | 0 |  |  | 23592.5841 | 5000 | 5000 | 5000 | 5000 |  | 2500 | 2500 |  |  |  | 5000 | 5000
1.1.4 | Forestry Report Launch Events etc | Media including TV, Radio, events and activities includign press release | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased knowledge of Forestry extractives in Myanmar | No. of events, TV /Radio Programs/ Media Articles No. and details of participants and audiences (gender, geographical location, ethnicity etc) Event Reports / quaility (accuracy of media reports) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
1.1.5 | Public Debates | Public Gathering/Debate and Road Show | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased knowledge of EITI and extractives in Myanmar | No. of public gatherings, debates, roadshow events No. and details of participants Event Feedback and Reports | 6815.1016 | 0 | 0 | 0 | 0 | 4062.1016 | 4062.1016 | 2753 |  |  |  | 0 |  |  |  | 0 | 2753 | 0 | 0 |  | 0 |  |  | 6815.1016 | 0 | [9 empty] | 0
1.1.6 | Prints and Publication | Other prints and IEC material development | NCS Communication, Communication and Outreach Sub-Committee | Goods | IEC Materials | No and type of materials produced No and type of materails distributed/ viewed online Feedback on materials (?) | 18866.3617 | 0 | 2706.2626 | 2736.0684 | 0 | 1230.0308 | 6672.3617 |  | 4964 | 1630 |  | 1630 |  |  |  | 0 | 6594 | 0 | 0 | 1538.9125 | 1538.9125 |  |  | 14805.2742 | 4061.0875 | 5600 | 5600 | 5600 |  | 5600 |  |  |  |  | 5600 | 3660 | Will remail 1060 after paid printing cost 2600 | 401.0875
1.1.7a. | Website | Redesign, regular update and maintenance MEITI Website & on-line library | NCS Communication, Communication and Outreach Sub-Committee | Non Consulting Services | Website | No. of hits on website Feedback Survey Validation Comments | 5097.565 | 575.4544 | 1279.7946 | 0 | 2642.3161 |  | 3922.1106 |  |  |  |  | 0 | 442 |  |  | 442 | 442 | 0 | 9 |  | 9 |  |  | 4948.565 | 149 | 149 |  |  |  | 158 |  |  |  |  | 158 | 1500 | To add ammount after confirmed communication | 1351
1.1.7b. | Video Production and Broadcasting | Video Production and Broadcasting | NCS Communication, Communication and Outreach Sub-Committee | Non Consulting Services | Videos | Number of views, boradcasts, feedback | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
1.1.8 | Web-portal and Infographic | Open data, Inforgraphic and updated data | NCS Communication, Communication and Outreach Sub-Committee | Non Consulting/ Consulting | Infographics and open data pages | No. of users Feedback and Validation Comments | 3000 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 3000 | 3000 | 3000 |  |  | 3000 |  |  |  |  | 3000 | 3000
1.1.10 | National EITI Conference | National EITI Conference | NCS Communication, Communication and Outreach Sub-Committee | Meeting and Workshop | Increased understanding of MEITI Improved multistakeholder participation Documented assessment of progress, Input for planning | Event Report No. and details of participants Progress assessment and Planning input Feedback from participants | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
Sub Total 1 | [6 empty] | 93241.1694 | 575.4544 | 3986.0572 | 2736.0684 | 16901.7903 | 5415.7991 | 29039.715 | 22140 | 7065 | 1630 | 7941 | 9571 | 442 | 0 | 0 | 442 | 39218 | 0 | 9 | 1538.9125 | 1547.9125 | 0 | 0 | 70381.0819 | 22860.0875 | 24399 | 24250 | 21250 | 0 | 21908 | 2500 | 0 | 0 | 0 | 24408 | 20660
Objective 2: To create an enabling environment for the effective implementation of the EITI Standard
2.1 | HR, Operation and Office Administration
2.1.1 | MOBD Operational Cost | MOBD Staff travel and Office Supplies | MOBD | Operating Cost/ Goods | Project Financial Management, Procurement and Grant Compliance | FM reports to MSG and Donors, Procurement Plans and Documentation OAG Audit LC and WC Support to EITI process | 114623 | 2101 | 1543 | 1253 | 2683 | 1709 | 7188 | 1825 | 2342 | 1081.21 | 947 | 2028.21 | 469 | 320 | 790 | 1579 | 7774.21 | 708 | 655 | 1036.2241 | 2399.2241 | 196.5997 | 470.2462 | 20129.2801 | 94493.7199 | 96204 | 96859 | 96859 |  | 3000 | 3000 | 3000 | 22300 | 65559 | 96859 | 94494
2.1.2 | NCS Operation Cost -Salaries | NCS Staff Salaries | NCS | Operating Cost | Successful Implementation of Work Plan activities | APR EITI Reconciliation Reports MSG and Subcommittee Minutes Staff Performance Evaluations | 589182.106 | 43920.6314 | 65176.2842 | 13117.5879 | 71704.6044 | 13651.818 | 163650.2945 | 52516 | 34762 | 40605.18 | 26566 | 67171.18 |  | 15409 |  | 15409 | 169858.18 | 28386 | 15191 | 14858.737 | 58435.737 | 28811.2022 | 14067.5286 | 478743.5739 | 110438.5321 | 168176 | 168116 | 168116 |  | 42000 | 60000 | 66116 |  |  | 168116 | 110439
2.1.3a | NCS Operation Cost | NCS Overheads ( Utilities, Travel, Communication service, Maintenance, Stationary, consumable material and other miscellaneous) | NCS | Operating Cost | Successful Implementation of Work Plan activities | APR EITI Reconciliation Reports MSG and Subcommittee Minutes | 136625.3707 | 10438.0187 | 21284.5961 | 0 | 17263.446 | 0 | 38548.0421 | 14988 | 7041 | 7076.04 | 7238 | 14314.04 |  | 5213 |  | 5213 | 41556.04 | 5668 | 2239.27 | 1061.5865 | 8968.8565 | 386.5302 | 239.4874 | 100136.9748 | 36488.3959 | 38176 | 38658 | 38658 |  | 8475 | 12000 | 18183 |  |  | 38658 | 36488
2.1.3b. | Consultant support service | Additional Travel and Accommodation costs to support consultants (BO, Cadastre etc) | NCS | Operating Cost | Facilitation of Consultants' Work | Consultant Deliverables | 3215.3194 | 0 | 0 | 0 | 777.3194 | 0 | 777.3194 |  | 1650 |  | 788 | 788 |  |  |  | 0 | 2438 | 0 | 0 |  | 0 |  |  | 3215.3194 | 0 | [9 empty] | 0
2.1.4 | NCS Operation Cost - Rent | NCS Office Rental | NCS | Operating Cost | Office Space | Office Rental Contract and Payment Reciept | 88193.1054 | 9031.9439 | 12382.2615 | 0 | 36000.9 | 0 | 48383.1616 |  |  |  | 30778 | 30778 |  |  |  | 0 | 30778 | 0 | 0 |  | 0 |  |  | 88193.1054 | 0 |  |  | 0 | [6 empty] | 0
2.1.5 | Office Set Up Cost | Equipment and Furniture | NCS, MOBD | Goods | Furniture and Equipment | Purchase Receipts Procurement Report Inventory | 32492.7881 | 9958.6036 | 4526.1845 | 0 | 0 | 0 | 4526.1845 |  |  |  | 17677 | 17677 | 324 |  |  | 324 | 18001 | 0 | 7 |  | 7 |  |  | 32492.7881 | 0 | 0 |  | 0 | 0 | [5 empty] | 0
2.1.6 | Fund raising- Advocacy | Secure increased government contribution to EITI | MOBD, MSG | Non Consulting |  |  | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
2.1.7 | MSG Meeting | MSG Meeting | NCS | Workshop and Meeting | MSG Meeting Decisions and Outputs (approved TOR, reports etc) | Meeting Minutes Approved (Myanmar and English) Minutes posted on MEITI Website Funds Raised | 78709.2271 | 8192.0498 | 23326.0527 | 3048.5487 | 7020 | 3807.5759 | 37202.1773 | 6602 | 3376 | 6105 | 3598 | 9703 |  |  |  | 0 | 19681 | 7134 | 0 | 3636.7787 | 10770.7787 |  |  | 75846.0058 | 2863.2213 | 6500 | 6500 | 6500 |  |  | 6500 |  |  |  | 6500 | 3000 |  | 137
2.1.8 | Sub-committee Meeting | MSG Sub-Committee Meetings | NCS | Workshop and Meeting | Subcommittee Meeting Recommendations and Outputs (draft TOR, reports etc) | Meeting Minutes Approved (Myanmar and English)Minutes posted on MEITI Website Funds Raised | 24609.6681 | 3767.6924 | 2866.3571 | 2961.752 | 2398.335 | 2794.5316 | 11020.9757 | 2233 | 3108 | 732 | 713 | 1445 | 133 |  | 200 | 333 | 7119 | 0 | 218 | 979.5944 | 1197.5944 |  |  | 23105.2625 | 1504.4056 | 2484 | 2702 | 2702 |  | 1400 | 1302 |  |  |  | 2702 | 3385 |  | 1881
2.1.8 a | Work Plan Review Workshop | [5 empty] | 2400 | [9 empty] | 2400 | 2400 |  |  |  | 0 | 2400 | 0 | 0 |  | 0 |  |  | 2400 | 0 | [9 empty] | 0
2.1.8 b | EITI Awareness Meeting | [5 empty] | 537 | [9 empty] | 537 | 537 |  |  |  | 0 | 537 | 0 | 0 |  | 0 |  |  | 537 | 0 | [9 empty] | 0
2.1.9 | Translation Fee for related documents | [5 empty] | 15493 | 2515 | 3691 | 1066 | 461 | 0 | 5218 | 3603 | 810 | 232 |  | 232 | 3115 |  |  | 3115 | 7760 | 0 | 0 |  | 0 |  |  | 15493 | 0 | [9 empty] | 0
Sub Total 2.1 | [6 empty] | 1086080.5849 | 89924.9397 | 134795.7361 | 21446.8887 | 138308.6048 | 21962.9256 | 316514.1552 | 81767 | 53089 | 55831.43 | 91242 | 147073.43 | 4041 | 20942 | 990 | 25973 | 307902.43 | 41896 | 18310.27 | 21572.9208 | 81779.1908 | 29394.3321 | 14777.2623 | 840292.31 | 245788.2748 | 311540 | 312835 | 312835 | 0 | 54875 | 82802 | 87299 | 22300 | 65559 | 312835 | 247806
2.2 | Workplan and Governance (APR, M&E- Review workshops)
2.2.1 | M&E Workshop | Review of annual progress (workplan), produce annual activity/progress report. | NCS, MSG | Workshop and Meeting | Increased understanding of MEITI Improved multistakeholder participation Documented assessment of progress, Input for planning | Event Report No. and details of participants Progress assessment and Planning input Feedback from participants | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
2.2.4 | Implementation of EITI report Recommendations Workshop | Workshop to develop the workplan for implementation of EITI recommendations | MOBD, NCS, Subcommittee, MSG | Workshop and meeting | Systematic assessment of EITI Recommendations from reports and planning for their implementation | SMART Work Plan for implementation Recommendations | 2444.3111 | 0 | 0 | 0 | 2444.3111 | 0 | 2444.3111 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 2444.3111 | 0 | [9 empty] | 0
2.2.5 | MSG Governance Review Workshop | MSG Reform and Selection | NCS, MSG, Government Agencies | Workshop and meeting/ Consultancy/ Goods | Outputs according to the agreed work plan | Indicators according to the agreed work plan | 5238 | 0 | 3224 | 0 | 0 | 0 | 3224 |  | 2014 |  |  | 0 |  |  |  | 0 | 2014 | 0 | 0 |  | 0 |  |  | 5238 | 0 | [9 empty] | 0
2.2.5 a | EITI Restructure Review | Implementation of EITI restructuring | MOBD, NCS, Subcommittee, MSG, Government Agencies | Workshop and meeting/ Consultancy/ Goods |  |  | 0 | [10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
2.2.6 | SOE Reform Workshop | SOE workshop, Pre-meeting on SOE situations and future reform plans for extractor sector | MOBD, NCS, Subcommittee, MSG | Workshop and Meeting | Increased awareness of MEITI Report recommendtions on SOE Reform Documented multi-stakeholder review of current SOE reform plans, achievements and challenges Plans for ongoing reforms and their coordination with MEITI | Workshop Report incl participation Documentation of assessments, decisions and plans | 12115 | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 5456 |  | 1222 | 1222 |  | 1284 |  | 1284 | 8232 | 0 | 0 |  | 0 |  |  | 8232 | 3883 | 3883 | 3883 | 3883 |  |  | 3883 |  |  |  | 3883 | 3883
2.2.7 | Validation | Data Collection and Stakeholder Consultation workshops for initial assessment /Validation Group Meeting and Consultation Meeting for 12 Correction Action | NCS, MSG | Workshop and meeting | Multistakeholder assessment and documentation of MEITI process Capacity Building for MEITI Stakeholders | Validation Report | 9487.9419 | 0 | 0 | 0 | 2957.9419 | 0 | 2957.9419 | 2330 |  |  |  | 0 |  |  |  | 0 | 2330 | 0 | 0 |  | 0 |  |  | 5287.9419 | 4200 | 4200 | 4200 | 4200 |  | 1050 | 1050 | 1050 | 1050 |  | 4200 | 4200
2.2.8 | Validation | Contribution to International Secretariat | MOBD, NCS |  | Payment made | Money transfer receipt, Bank Transaction Sheet, letter of acknowledgement from EITI | 10000 | 0 | 0 | 0 | 0 | 10000 | 10000 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 10000 | 0 | [9 empty] | 0
Sub Total 2.2 | [6 empty] | 39285.2531 | 0 | 3224 | 0 | 5402.2531 | 10000 | 18626.2531 | 2600 | 7470 | 0 | 1222 | 1222 | 0 | 1284 | 0 | 1284 | 12576 | 0 | 0 | 0 | 0 | 0 | 0 | 31202.2531 | 8083 | 8083 | 8083 | 8083 | 0 | 1050 | 4933 | 1050 | 1050 | 0 | 8083 | 8083
2.3 | Sub-National Coordination Unit (Formation and Functioning)
2.3.1 | SNU Formation and Coordination | Establishing Sub-National Coordination Units at State and Division level and further coordination with Union EITI. | NCS, MSG, Communication Officer | Workshop and meeting | SNUs Formed (Membership, TOR) Meeting Records / Minutes/ Reports | No. of SNUs Formed SNU Membership details (inclusivity, participation, geographic coverage) SNU TORs and Work Plans | 34749.2633 | 0 | 10632.5588 | 0 | 10549.19 | 3180.5145 | 24362.2633 | 10387 |  |  |  | 0 |  |  |  | 0 | 10387 | 0 | 0 |  | 0 |  |  | 34749.2633 | 0 | [9 empty] | 0
2.3.2 | Coordination between MSG and SNUs | Review and evaluate reports from SNUs and determine coordinate consistent response to issues raised. MSG to establish internal monitoring and evaluation mechanism on workplan implementation?? | NCS, MSG, SNU |  | ??? | ??? | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
Sub Total 2.3 | [6 empty] | 34749.2633 | 0 | 10632.5588 | 0 | 10549.19 | 3180.5145 | 24362.2633 | 10387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10387 | 0 | 0 | 0 | 0 | 0 | 0 | 34749.2633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total 2 |  |  |  | Sub Total 2 |  |  | 1160115.1012 | 89924.9397 | 148652.2949 | 21446.8887 | 154260.0478 | 35143.4401 | 359502.6715 | 94754 | 60559 | 55831.43 | 92464 | 148295.43 | 4041 | 22226 | 990 | 27257 | 330865.43 | 41896 | 18310.27 | 21572.9208 | 81779.1908 | 29394.3321 | 14777.2623 | 906243.8264 | 253871.2748 | 319623 | 320918 | 320918 | 0 | 55925 | 87735 | 88349 | 23350 | 65559 | 320918 | 255889
Objective 3:To support implementation of sustainable development and natural resource governance reforms through the successful execution of EITI.
3.1 | Technical and Reporting (IA main report, Forestry, BO, Mining Cadaster, SOE, Review of Artisenal Mining, Fasibility studies, Sub-national study, Implementation of recommendations, & other technical studies)
3.1.1 | Legislative institutionalization | Research to recommend legal options to EITI institunalization. Developing a draft EITI Law or amemdments to Sectoral Laws | NCS, Subcommittee, MSG | Consultancy | Research Report and Recommendations | Research Report and Recommendations accpeted by MSG | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.3 | EITI Reconciliation Report 2 &3 | [5 empty] | 270890 | 110740 | 83055 | 0 | 0 | 0 | 83055 | 77095 |  |  |  | 0 |  |  |  | 0 | 77095 | 0 | 0 |  | 0 |  |  | 270890 | 0 | [9 empty] | 0
3.1.3 | EITI Reconciliation Report 4 | [5 empty] | 248084 |  | 0 | 0 | 0 | 0 | 0 |  | 173898 | 74186 |  | 74186 |  |  |  | 0 | 248084 | 0 | 0 |  | 0 |  |  | 248084 | 0 | [9 empty] | 0
3.1.3 | EITI Reconciliation Report 5 | Independent Administrator and procure firm each year for the annual report (including scoping study) | MOBD, NCS, IA | Consulting | EITI Reconciliation Reports | Reports produced by deadline Reports approved by MSG Validation results on EITI Standard 2-6 | 370460 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 148184 |  | 148184 | 222276 | 370460 | 370460 | 370460 |  | 370460 |  |  |  |  | 370460 | 222276
3.1.3 | EITI Reconciliation Report 5 | [5 empty] | 0 | [10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.3 | EITI Reconciliation Report 6 | [5 empty] | 0 | [10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.3 b | EITI Reconciliation Report Workshops | Report reconciliation and Reporting entities workshops-Main IA |  |  |  |  | 21543.4513 | 4439.4513 | 10484 | 0 | 0 | 0 | 10484 | 4744 | 1876 |  |  | 0 |  |  |  | 0 | 6620 | 0 | 0 |  | 0 |  |  | 21543.4513 | 0 | [9 empty] | 0
3.1.3 c | EITI Report Template Training | Template Training with IA and respective Agency |  |  |  |  | 7113 | [10 empty] | 0 |  |  | 140 | 140 | 140 | 3764 | 2165 |  | 5929 |  |  | 6069 | 1044 | 1044 | [8 empty] | 0 | 1044
3.1.4 a | Forestry Reconciliation Report-1 | IA - First report |  | Consulting | Forestry Reconconciliation Report(s) | Report(s) approved by MSG | 160000 | 0 | 48000 | 80000 | 0 | 0 | 128000 |  |  | 32000 |  | 32000 |  |  |  | 0 | 32000 | 0 | 0 |  | 0 |  |  | 160000 | 0 | [9 empty] | 0
3.1.4 b | Forestry Reconciliation Report-2 | IA - First report |  |  |  |  | 0 | 0 |  |  | 0 | 0 | [5 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.4 c | Forestry Reconciliation Report Workshops | Reporting entities workshops-Forestry IA |  |  |  |  | 3952.4048 | 0 | 3952.4048 | 0 | 0 | 0 | 3952.4048 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 3952.4048 | 0 | [9 empty] | 0
3.1.4 d | Hydro Reconcillation Report | Independent Administrator and procure firm each year for the annual report (including scoping study) |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
| Hydro Reconcillation Report Meetings | [5 empty] | 223 |  | 0 | 0 | 0 | 0 | 0 | 223 |  |  |  | 0 |  |  |  | 0 | 223 | 0 | 0 |  | 0 |  |  | 223 | 0 | [9 empty] | 0
3.1.5 | Mineral and Gemstone Cadaster Phase 1 Consultant | Design Phase | MONREC, NCS, Subcommitte, MSG | Consulting | Preliminary, Intermediate and Final Report Mineral Cadastre Conceptual Design TOR for Phase 2 | Documents received and approved by MONREC and MSG | 119125.15 | 40017 | 40024 | 0 | 39084.15 | 0 | 79108.15 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 119125.15 | 0 | [9 empty] | 0
3.1.6 a | Mineral and Gemstone Pre-Cadastre Consultant | Pre-cadaster Working Group Consultant | MONREC, NCS, Subcommitte, MSG | Consulting | Training and on the job support Precadastre developed | No. of staff trained No. of Training Hours completed Completeness of Precadastre | 41390 | 0 | 0 | 0 | 12600 | 0 | 12600 | 15000 |  | 13790 |  | 13790 |  |  |  | 0 | 28790 | 0 | 0 |  | 0 |  |  | 41390 | 0 | [9 empty] | 0
3.1.6 b | Office Set Up Equipment for Pre Cadaster Working | [5 empty] | 21980.74 | 0 | 0 | 0 | 0 | 18168.74 | 18168.74 |  | 983 | 2771 | 58 | 2829 |  |  |  | 0 | 3812 | 0 | 0 |  | 0 |  |  | 21980.74 | 0 | [9 empty] | 0
3.1.6 c | Office Set up-Furniture for Pre-Cadastre working group | [5 empty] | 5632.769 | 0 | 0 | 0 | 0 | 3259.769 | 3259.769 |  | 2373 |  |  | 0 |  |  |  | 0 | 2373 | 0 | 0 |  | 0 |  |  | 5632.769 | 0 | [9 empty] | 0
3.1.6 d | ARC,GIS Software | [5 empty] | 40000 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 40000 | 0 |  | 40000 |  |  | 40000 | 0 | [9 empty] | 0
3.1.6 e | Maps, Stationery | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
| Gemstone Mapping Consultant | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.7 | Mineral and Gemstone Cadaster Phase 2 Consultant | Development and installation of cadaster. | MONREC, NCS, Subcommitte, MSG | Consulting | Deliverables outlined in TOR for Phase 2 | Indicators according to deliverables from TOR Phase 2 | 670000 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 670000 | 670000 | 670000 | 670000 |  | 134000 | 134000 | 134000 | 134000 | 134000 | 670000 | 670000
3.1.8 | Mineral and Gemstone Cadaster Equipment | Purchase of IT equipment and furniture | MONREC, NCS, MOBD | Goods | Equipment and Furniture | Procurement report Purchase Receipt Inventory | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.11a. | Beneficial Ownership (ASI) | Development of Workplan, Communicaiton Plan, Capacity Building Plan and Pilot Project | NCS, Subcommittee, MSG | Consultancy | BO Work Plan, BO Communications Plan, BO Capacity Development Plan, BO Pilot Project | Deliverables approved by MSG | 120000 | 0 | 36000 | 0 | 0 | 84000 | 120000 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 120000 | 0 | [9 empty] | 0
3.1.11b. | Beneficial Ownership (Matheiu) | BO Template |  |  |  |  | 5685 | [9 empty] | 5685 | 5685 |  |  |  | 0 | 5685 | 0 | 0 |  | 0 |  |  | 5685 | 0
3.1.12 | Beneficial Ownership Meetings | BO workshops and Taskforce Meetings/ Template Training/ BO Press Condference | NCS, Task Force | Meeting and Workshop |  | No. of workshop/ meeting | 23824.3925 | 0 | 0 | 3657.1034 | 2001.05 | 6301.239 | 11959.3925 | 898 |  | 3260 | 2205 | 5465 |  |  |  | 0 | 6363 | 1002 | 0 | 1688.9575 | 2690.9575 |  |  | 21013.35 | 2811.0425 | 4500 | 4500 |  |  | 4500 |  |  |  |  | 4500 | 3500 |  | 689
3.1.12 a | Beneficial Ownership | [5 empty] | 6525 | [9 empty] | 5998 | 5998 |  |  | 527 | 527 | 6525 | 0 | 0 |  | 0 |  |  | 6525 | 0 | [9 empty] | 0
3.1.12 c | Beneficial Ownership (Online Disclosure Form) | Development of Beneficial Ownership discloure Online system | DICA | Non Consulting Services |  |  | 8000 | [10 empty] | 0 |  |  | 7607 | 7607 | 7607 | 0 | 155 |  | 155 |  |  | 7762 | 238 | 238 |  |  |  | 393 |  |  |  |  | 393 | 0 | Reduce as no activity | 238
3.1.14a. | Systematic Disclosure Feasibility Study | [5 empty] | 0 | [10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.1.4b | Systematic Disclosure Consultancy | [5 empty] | 0 | [10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
Sub Total 3.1 | [6 empty] | 2144428.9075 | 155196.4513 | 221515.4048 | 83657.1034 | 53685.2 | 111729.748 | 470587.4562 | 97960 | 179130 | 126007 | 13946 | 139953 | 0 | 0 | 8274 | 8274 | 425317 | 44766 | 2320 | 1688.9575 | 48774.9575 | 148184 | 0 | 1248059.865 | 896369.0425 | 1046242 | 1044960 | 1040460 | 0 | 509353 | 134000 | 134000 | 134000 | 134000 | 1045353 | 896820
3.2 | Training and Capacity Development (Capacity Development for 3 MSG entities, MOBD, NCS & SNU capacity building)
3.2.1 a | Capacity Development | Implement Capacicty Development Plan (MSG, Private Sector, Governemnt, CSO, Media, EAOs, MOBD, NCS, Parliament and others) | NCS, MSG | Meeting and Workshop | Outputs defined in capacity development plan | Indicators defined in Capacity Development Plan Incld No. of participants, participant criteria (gender, stakeholder group, geographic location etc) Participant feedback | 33729.5837 | 8267.6968 | 4147.6666 | 720.018 | 11964.2991 | 8629.9032 | 25461.8869 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 33729.5837 | 0 | [9 empty] | 0
3.2.1 b | Capacity Development for Awareness | EITI Standard Awareness |  | Workshop and meeting/ Consultancy/ Goods |  |  | 0 | [10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.2.2 | Corrective Action Planning and Workshop | Corrective Actions and recommendation, SOE workshop, follow up action | NCS, Subcommittee, MSG | Workshop and meeting/ Consultancy/ Goods |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | [9 empty] | 0
3.2.3 | Capacity Development- Study Tour | MSG Study Tours | MSG | Non Consulting | Outputs defined in Study Tour Concept Note or Plan | Indicators from concpet note or plan Incld No. of participants, participant criteria (gender, stakeholder group, geographic location etc) Participant feedback and cascading activities | 24584.7365 | 0 | 0 | 0 | 12702.7365 | 0 | 12702.7365 |  | 567 |  | 11046 | 11046 |  |  |  | 0 | 11613 | 0 | 0 |  | 0 |  |  | 24315.7365 | 269 | 269 | 269 |  |  | 269 |  |  |  |  | 269 | 0 | Reduce as no activity | 269
3.2.4 | Capacity Development- Int'l EITI events | EITI Global/ Regional Conferences and Board Meetings | MSG | Non Consulting | EITI Internnational Events attended | No. of events attended, No. of participants, cascade activities | 13380 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 12256 | 1124 | 13380 |  |  |  | 0 | 13380 | 0 | 0 |  | 0 |  |  | 13380 | 0 | [9 empty] | 0
3.2.5 | Financial Management Training (MOBD/NCS) | MOBD Financial management capacity development | NCS, Subcommittee, MSG | Consulting | Training and on the job support | No. of MOBD staff trained | 30520.8979 | 0 | 5969.7164 | 0 | 9261.1815 | 0 | 15230.8979 |  |  |  | 15290 | 15290 |  |  |  | 0 | 15290 | 0 | 0 |  | 0 |  |  | 30520.8979 | 0 | [9 empty] | 0
Sub Total 3.2 | [6 empty] | 102215.2181 | 8267.6968 | 10117.383 | 720.018 | 33928.2171 | 8629.9032 | 53395.5213 | 0 | 567 | 12256 | 27460 | 39716 | 0 | 0 | 0 | 0 | 40283 | 0 | 0 | 0 | 0 | 0 | 0 | 101946.2181 | 269 | 269 | 269 | 0 | 0 | 269 | 0 | 0 | 0 | 0 | 269 | 0
Sub Total 3 |  |  |  | Sub Total 3 |  |  | 2246644.1256 | 163464.1481 | 231632.7878 | 84377.1214 | 87613.4171 | 120359.6512 | 523982.9775 | 97960 | 179697 | 138263 | 41406 | 179669 | 0 | 0 | 8274 | 8274 | 465600 | 44766 | 2320 | 1688.9575 | 48774.9575 | 148184 | 0 | 1350006.0831 | 896638.0425 | 1046511 | 1045229 | 1040460 | 0 | 509622 | 134000 | 134000 | 134000 | 134000 | 1045622 | 896820
GRAND TOTAL |  |  |  | Grand Total |  |  | 3500000.3962 | 253964.5421 | 384271.1398 | 108560.0785 | 258775.2552 | 160918.8905 | 912525.364 | 214854 | 247321 | 195724.43 | 141811 | 337535.43 | 4483 | 22226 | 9264 | 35973 | 835683.43 | 86662 | 20639.27 | 24800.7907 | 132102.0607 | 177578.3321 | 14777.2623 | 2326630.9913 | 1173369.4049 | 1390533 | 1390397 | 1382628 | 0 | 587455 | 224235 | 222349 | 157350 | 199559 | 1390948 | 1173369 |  | 0.40486
| TOTAL (July 2019 to 13th May 2020) | [16 empty] | 697966.0851
Note on B70: To be funded from the 500 K Cost Exptension

## Budget_Category
Budget Category in Remaining 3.5 Million(2-6-2020)
1 | Implementation Cost
| Communication and Outreach | 4th Report Printing and Translation | 7500
|  | 4th Report Launch | 5000
|  | 2019 EITI Standard Translation and Printing | 3660
|  | MEITI Website Maintainance | 1500
| MSG, Sub-Committee, BO, Training, Workshop, Meeting | MSG Meeting | 3000
|  | Sub Committee Meeting | 3385
|  | BO Task Force Meeting and Training | 3500
|  | Validation Group Meeting | 4200
|  | SOE Workshop | 3883
|  | Template Training and Meeting | 1044
| Sub- Total |  | 36672
2 | EITI Secretariat Office Running Cost
| Operation Cost and Salary | MOBD Operation Cost | 94494
|  | NCS Office Salary | 110439
|  | NCS Office Operation Cost | 36488
| Sub- Total |  | 241421
3 | Consult Fees
| IA, Mining Cadaster, Web Portal | Mining Cadaster Phase II Consultant Fees | 670000
|  | 5th Report and Forestry Report IA Conusltant Fees | 222276
|  | Web Portal and Infographic Consultant Fees | 3000
| Sub- Total |  | 895276
| Total |  | 1173369